## Quality Maturation Plan (2)
QUALITY MATURATION PLAN FOR CHANGE POINT ISD-QA-048
Month |  |  |  |  | PP-1 | [15 empty] | PP-2 | [11 empty] | PP-3 | [7 empty] | MASS PRODUCTION REDINESS
[5 empty] | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2017-01-01 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
SR. NO | PART. | CHANGE POINT | ACTIVITY
1 | GSDN | 1. MATERIAL CHANGE SCM 420 → S53C | GRAIN SIZE AND GRAIN FLOW INSPECTION AT SOFT AND HARD STAGE | PLAN
ACTUAL
|  | 2. HEAR TREATMENT CARBURISING → INDUCTION HARDNING | 9 POINT STUDY | PLAN
ACTUAL
|  |  | LEAD & PROFILE DISTORTION STUDY | PLAN
ACTUAL
2 | GEAR RS | 1.MATERIAL CHANGE SCM420→SCR420 | GRAIN SIZE AND GRAIN FLOW INSPECTION AT SOFT AND HARD STAGE | PLAN
ACTUAL
|  | 2.INSIDE HARNESS HRC30~45 →HRC 25~45 | 9 POINT STUDY | PLAN
ACTUAL
|  |  | LEAD AND PROFILE DISTORTION STUDY | PLAN
ACTUAL
|  | 3.IDENTIFICATION MARK IDENT MARK DEPRESS 0.5 MM | EXECUTE TRAINING FOR ALL LINE OPERATOR AGAINST THAT IDENTIFICATION MARK | PLAN
ACTUAL
|  |  | UPDATION IN FINAL INSPECTION STANDARD WITH IDENTIFICATION MARK | PLAN
ACTUAL
3 | GEAR PKS | 1.MATERIAL CHANGE SCM420→SCR420 | GRAIN SIZE AND GRAIN FLOW INSPECTION | PLAN
ACTUAL
|  | 2.INSIDE HARNESS HRC30~45 →HRC 25~45 | 9 POINT STUDY | PLAN
ACTUAL
|  |  | LEAD AND PROFILE DISTORTION STUDY | PLAN
ACTUAL
|  | 3.IDENTIFICATION GROOVE MARK OMIT | TRAINING ORGANISE AGAINST REMOVAL OF IDENTIFICATION MARK | PLAN
ACTUAL
|  |  | NEED TO UPDATE FINAL INSPECTION STANDARD AGANIST THAT REMOVAL OF IDENT MARK | PLAN
ACTUAL
4 | GEAR M-4 | 1.BORE DIA 20 H7 (+0.021/ 0) MM →17 H7 (+0.018/ 0) MM | BORE DIA CP & CPK STUDY | PLAN
ACTUAL
|  | 2.ROOT DIA. 42.1 MM →41.9 MM | ROOT DIA SPC STUDY | PLAN
ACTUAL
|  | 3. SINGLE DOT MARK ADDED | EXECUTE TRAINING FOR ALL LINE OPERATOR AGAINST THAT IDENTIFICATION MARK | PLAN
ACTUAL
|  |  | ADDITION IN FINAL INSPECTION STANDARD WITH IDENTIFICATION MARK | PLAN
ACTUAL
5 | GEAR GKIS | 1.MATERIAL CHANGE SCM420→SCR420 | GRAIN SIZE AND GRAIN FLOW INSPECTION AT SOFT AND HARD STAGE | PLAN
ACTUAL
|  | 2.INSIDE HARNESS HRC30~45 →HRC 35~45 | 9 POINT STUDY | PLAN
ACTUAL
|  |  | LEAD AND PROFILE DISTORTION STUDY | PLAN
ACTUAL
|  | 3.IDENTIFICATION MARK IDENT MARK DEPRSS 0.3MM | TRAINING ORGANISE AGAINST THAT IDENTIFICATION MARK | PLAN
ACTUAL
|  |  | ADDITION IN FINAL INSPECTION STANDARD WITH IDENTIFICATION MARK | PLAN
ACTUAL
[8 empty] | Prepaired | [20 empty] | Checked | [18 empty] | Approved
PP-1
8-June
PP-2
21-Oct
PP-3
13-Jan
MP
4-Feb