## MTP WEGO 25.07.17 (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [57 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [33 empty] | 1 | 25.07.17 | [6 empty] | Praveen |  |  |  | SUNDAR K | [9 empty] | FC | Santosh San
Year : | 2016-17 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | FC |  |  | ME |  |  | Production |  |  | Quality |  | Purchase |  |  |  |  | 0 | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [9 empty] | ME | Narendra San
Customer : | TVSM | [39 empty] | REV | Remarks | [6 empty] | Prepared |  |  |  | Approved | [9 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [11 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Cust Event | bar: 2017-10-16 W3
PRODUCTS |  |  | CUSTOMER EVENT | [59 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-11-01 W1: T0; 2017-12-01 W3: T1; 2018-01-01 W3: PL1; 2018-01-01 W4: MP
[63 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY | bar: 2017-10-16 W3
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-11-01 W1: 25; 2017-12-01 W3: 100; 2018-01-01 W3: 1000; 2018-01-01 W4: 200; 2018-02-01 W1: 200; 2018-02-01 W2: 200; 2018-02-01 W3: 200; 2018-02-01 W4: 200; 2018-03-01 W1: 400; 2018-03-01 W2: 400; 2018-03-01 W3: 400; 2018-03-01 W4: 400
ACTUAL
|  |  |  | Go Ahead from the customer | QA-BLR | PLAN | 2017-11-01 w2: For T1 & PL1
ACTUAL
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-10-16 W3; 2017-11-01 w2
ACTUAL
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-10-16 W3; 2017-11-01 w2
ACTUAL
|  |  |  | Forjing Sozai order | FC-BLR | PLAN | 2017-11-01 w2: For T1 & PL1; 2017-11-01 W5: MP
ACTUAL
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | 2017-11-01 W5: For T1 & PL1; 2018-01-01 W1: MP
ACTUAL
|  |  |  | Inspection | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  |  |  | making | ME-BLR | PLAN | bar: 2017-10-16 W1 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W2; 2017-12-01 W4 to 2018-01-01 W4
ACTUAL
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE | bar: 2017-10-16 W3
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN | bar: 2017-10-16 W3
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5; 2017-10-16 W3
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2; 2017-10-16 W3
ACTUAL
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN | bar: 2017-10-16 W3
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Lack rolling machine | ME-BLR | PLAN | 2017-08-16 W3: fin.; 2017-08-16 W4: move; 2017-08-16 W5: set up; 2017-09-16 W2: trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W2: set up; 2017-08-16 W4: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-07-16 W3
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W3: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 w2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  | 3.Tools & Measurement equipments |  | Tool list | PE-BWL | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W1; 2017-10-16 W3
ACTUAL | bar: 2017-07-16 W1 to 2017-07-16 W3
|  |  |  | A'Class tool design & arrangement (broach,hob shaving Frazing cutter and honing tool) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W4
ACTUAL | bar: 2017-07-16 W3
|  |  |  | A Class tooling PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-08-16 W5
ACTUAL
|  | 3.Jigs |  | Jigs list, design & Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W4; 2017-10-16 W3
ACTUAL
|  | 3a. Guages |  | Spcl Guages List, design & manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W4; 2017-10-16 W3
ACTUAL
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-07-16 W2: Material Order; 2017-09-16 W2: Transport try
ACTUAL
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W1; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ②Lot control | Production | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W4; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2017-08-16 W5 to 2017-12-01 W2
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-08-16 W4; 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W2; 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-06-16 W1; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-06-16 W1; 2017-08-16 W3 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-04-16 W3 to 2017-05-16 W1; 2017-08-16 W3 to 2017-08-16 W5; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-03-16 W1 to 2017-04-16 W3; 2017-08-16 W3 to 2017-08-16 W4; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-03-16 W3 to 2017-04-16 W3; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  | 2.Prevention |  | ①Design verification | NA | PLAN | bar: 2017-04-16 W4 to 2017-05-16 W4; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-05-16 W4; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-05-16 W4 to 2017-07-16 W1; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-06-16 W1 to 2017-07-16 W1; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-05-16 W4 to 2017-06-16 W3; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-04-16 W4 to 2017-06-16 W3; 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-08-16 W5 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4; 2017-11-01 W5 to 2017-12-01 W2
ACTUAL
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2017-10-16 W3; 2017-11-01 W1 to 2017-11-01 W4; 2017-12-01 W1 to 2017-12-01 W2
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-10-16 W3; 2017-11-01 W5
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
ACTUAL
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2017-10-16 W2 to 2018-03-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-07-16 W3 to 2017-07-16 W4; 2017-08-16 W3 to 2017-08-16 W4; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W2 to 2017-10-16 W4
EVALUATION
|  |  | Check By |  |  |  | 2017-03-16 W1: SUNDAR KULKARNI; 2017-04-16 W1: SUNDAR KULKARNI; 2017-05-16 W1: SUNDAR KULKARNI; 2017-06-16 W1: SUNDAR KULKARNI; 2017-07-16 W1: SUNDAR KULKARNI; 2017-08-16 W1: SUNDAR KULKARNI; 2017-09-16 W1: SUNDAR KULKARNI; 2017-10-16 W1: SUNDAR KULKARNI; 2017-11-01 W1: SUNDAR KULKARNI; 2017-12-01 W1: SUNDAR KULKARNI; 2018-01-01 W1: SUNDAR KULKARNI; 2018-02-01 W1: SUNDAR KULKARNI; 2018-03-01 W1: SUNDAR KULKARNI
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2

## MTP WEGO Rev-1 27-7-17 (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [71 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [46 empty] | 1 | 25.07.17 | [6 empty] | Praveen |  |  |  | SUNDAR K | [10 empty] | FC | Santosh San
Year : | 2016-17 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD | [13 empty] | 0 | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [10 empty] | ME | Narendra San
Customer : | TVSM | [52 empty] | REV | Remarks | [6 empty] | Prepared |  |  |  | Approved | [10 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [25 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
Cust Event | bar: 2017-10-16 W3; 2017-12-01 W4
PRODUCTS |  |  | CUSTOMER EVENT | [73 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-11-01 W4: T0; 2018-03-01 W1: T1; 2018-04-01 W2: PL1; 2018-05-01 W1: MP
[77 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY | bar: 2017-10-16 W3; 2017-12-01 W4
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-11-01 W4: 25; 2018-03-01 W1: 100; 2018-04-01 W2: 1000; 2018-05-01 W1: 200; 2018-05-01 W2: 200; 2018-05-01 W3: 200; 2018-05-01 W4: 200; 2018-05-01 W5: 200
ACTUAL
|  |  |  | Go Ahead from the customer | QA-BLR | PLAN | bar: 2017-10-16 W3; 2017-12-01 W3 to 2017-12-01 W4
ACTUAL
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-10-16 W3; 2017-12-01 W3 to 2017-12-01 W4
ACTUAL
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-10-16 W3; 2017-12-01 W3 to 2017-12-01 W4
ACTUAL
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-10-16 W3; 2017-12-01 W3 to 2017-12-01 W4
ACTUAL
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2017-10-16 W3; 2017-12-01 W4; 2018-01-01 W4 to 2018-01-01 W5
ACTUAL
|  |  |  | Making | ME-BLR | PLAN | bar: 2017-10-16 W1 to 2017-11-01 W3; 2017-12-01 W4; 2018-02-01 W1 to 2018-02-01 W4; 2018-03-01 W2 to 2018-04-01 W1; 2018-04-01 W3 to 2018-05-01 W1
ACTUAL | bar: 2018-02-01 W4; 2018-04-01 W1; 2018-05-01 W1
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W3; 2017-12-01 W4
ACTUAL
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE | bar: 2017-10-16 W3; 2017-12-01 W4
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN | bar: 2017-10-16 W3; 2017-12-01 W4
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5; 2017-10-16 W3; 2017-12-01 W4
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2; 2017-10-16 W3; 2017-12-01 W4
ACTUAL
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN | bar: 2017-10-16 W3; 2017-12-01 W4
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Lack rolling machine | ME-BLR | PLAN | 2017-08-16 W3: fin.; 2017-08-16 W4: move; 2017-08-16 W5: set up; 2017-09-16 W2: trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W2: set up; 2017-08-16 W4: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-07-16 W3
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W3: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 w2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W3
|  | 3.Tools & Measurement equipments |  | Tool list | PE-BWL | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W1; 2017-10-16 W3; 2017-12-01 W4
ACTUAL | bar: 2017-07-16 W1 to 2017-07-16 W3
|  |  |  | A'Class tool design & arrangement (broach,hob shaving Frazing cutter and honing tool, GRINDING WHEEL, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep delay in drawing release.
ACTUAL | bar: 2017-07-16 W3
|  |  |  | A Class tooling PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-08-16 W5; 2017-10-16 W3; 2017-12-01 W4
ACTUAL
|  | 3.Jigs |  | Jigs list, design & Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W4; 2017-10-16 W3; 2017-12-01 W1 to 2018-01-01 W5
ACTUAL
|  | 3a. Guages |  | Spcl Guages List, design & manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W4; 2017-10-16 W3; 2017-12-01 W1 to 2018-01-01 W5
ACTUAL
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W4; 2017-12-01 W1 to 2017-12-01 W4; 2018-01-01 W4
ACTUAL
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-09-16 W2; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ②Lot control | Production | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-10-16 W1; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2017-08-16 W4 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2017-09-16 W1 to 2017-12-01 W4
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-08-16 W2 to 2017-08-16 W5; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-08-16 W3; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-06-16 W1; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-06-16 W1; 2017-08-16 W4 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-04-16 W3 to 2017-05-16 W1; 2017-08-16 W4 to 2017-09-16 W1; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-03-16 W1 to 2017-04-16 W3; 2017-08-16 W4 to 2017-08-16 W5; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-03-16 W3 to 2017-04-16 W3; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | 2.Prevention |  | ①Design verification | NA | PLAN | bar: 2017-04-16 W4 to 2017-05-16 W4; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-05-16 W1 to 2017-05-16 W4; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-05-16 W4 to 2017-07-16 W1; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-06-16 W1 to 2017-07-16 W1; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-05-16 W4 to 2017-06-16 W3; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-04-16 W4 to 2017-06-16 W3; 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W1 to 2017-12-01 W4
ACTUAL
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2017-10-16 W3; 2017-11-01 w2 to 2017-11-01 W5; 2017-12-01 W2 to 2017-12-01 W4
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-10-16 W3; 2017-12-01 W1; 2017-12-01 W4
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-10-16 W3; 2017-12-01 W4
ACTUAL
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
ACTUAL
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2017-10-16 W3 to 2018-06-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-07-16 W4 to 2017-08-16 W1; 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W3 to 2017-09-16 W4; 2017-10-16 W3 to 2017-11-01 w2; 2017-12-01 W4
EVALUATION
|  |  | Check By |  |  |  | 2017-03-16 W1: SUNDAR KULKARNI; 2017-04-16 W1: SUNDAR KULKARNI; 2017-05-16 W1: SUNDAR KULKARNI; 2017-06-16 W1: SUNDAR KULKARNI; 2017-07-16 W1: SUNDAR KULKARNI; 2017-08-16 W1: SUNDAR KULKARNI; 2017-09-16 W1: SUNDAR KULKARNI; 2017-10-16 W1: SUNDAR KULKARNI; 2017-11-01 W1: SUNDAR KULKARNI; 2017-12-01 W1: SUNDAR KULKARNI; 2018-01-01 W1: SUNDAR KULKARNI; 2018-02-01 W1: SUNDAR KULKARNI; 2018-03-01 W1: SUNDAR KULKARNI; 2018-04-01 W1: SUNDAR KULKARNI; 2018-05-01 W1: SUNDAR KULKARNI
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
For T1 & PL1
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Still some technical issue not clear from customer end, if its delayed, again event will postpone.
Note on G55: Author:

## MTP WEGO (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [75 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [73 empty] | FC | Praveen San
Year : | 2017-18 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [14 empty] | 0 | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [10 empty] | ME | Narendra San
Customer : | TVSM | [56 empty] | REV | Remarks | [6 empty] | Prepared |  |  |  | Approved | [10 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [29 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [77 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-11-01 W4: T-0; 2018-02-01 W2: T1; 2018-03-01 W2: PL1; 2018-03-01 W4: MP
[81 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-11-01 W4: 25; 2018-02-01 W2: 100; 2018-03-01 W2: 1000; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 200; 2018-04-01 W4: 200; 2018-05-01 W1: 400; 2018-05-01 W2: 400; 2018-05-01 W3: 400; 2018-05-01 W4: 400; 2018-05-01 W5: 400; 2018-06-01 W1: 400; 2018-06-01 W2: 400; 2018-06-01 W3: 400; 2018-06-01 W4: 400
ACTUAL
|  |  |  | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W3 to 2017-12-01 W4; 2018-02-01 W1
ACTUAL
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL
|  |  |  | Sample Making | ME-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 W3; 2018-01-01 W4 to 2018-03-01 W4
ACTUAL
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1; 2017-11-01 W3; 2018-02-01 W2; 2018-03-01 W2; 2018-03-01 W4
ACTUAL
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-07-16 W4
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Lack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-07-16 W4
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W4
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 w2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W4
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 w2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-07-16 W4
|  | 3.Tools & Measurement equipments |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W1
ACTUAL | bar: 2017-07-16 W1 to 2017-07-16 W4
|  |  |  | A'Class tool design (broach,hob shaving Frazing cutter and honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-07-16 W4
|  |  |  | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL
|  | 3.Jigs |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL
|  | 3.Jigs |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL
|  | 3a. Guages |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL
|  | 3a. Guages |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
[6 empty] | ACTUAL | 2018-01-01 W1: Packing for T1 trials; 2018-02-01 W2: Approval from Customer; 2018-03-01 W2: MP bin receive
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL
|  |  |  | ②Lot control | Production | PLAN | bar: 2017-10-16 W2 to 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-12-01 W4 to 2018-01-01 W2
ACTUAL
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W3; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W3
ACTUAL
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4; 2018-02-01 W4 to 2018-03-01 W2
ACTUAL
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-11-01 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W1
ACTUAL
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | 2.Prevention |  | ①Design verification | NA | PLAN
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W4 to 2018-01-01 W5; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2018-03-01 W1 to 2018-03-01 W4
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W3 to 2018-02-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-03-01 W4 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W3 to 2018-03-01 W4
EVALUATION
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
For T1 & PL1
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Some technical issue yet to clarify from TVSM. Event progressis based on clarifications & closure.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
QCD-3
T0 Event Process
T1 Event
PL1 Event
200 NOS PER DAY
400 NOS PER DAY

## MTP WEGO REV-1 (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [75 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 1 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [10 empty] | FC | Praveen San
Year : | 2017-18 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 0 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [10 empty] | ME | Narendra San
Customer : | TVSM | [53 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [10 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [29 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [77 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-11-01 W4: T-0; 2018-02-01 W2: T1; 2018-03-01 W2: PL1; 2018-03-01 W4: MP
[81 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-11-01 W4: 25; 2018-02-01 W2: 100; 2018-03-01 W2: 1000; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 200; 2018-04-01 W4: 400; 2018-05-01 W1: 600; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800
ACTUAL
|  |  |  | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W3 to 2017-12-01 W4; 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | Sample Making | ME-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 W3; 2018-01-01 W4 to 2018-03-01 W4
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1; 2017-11-01 W3; 2018-02-01 W2; 2018-03-01 W2; 2018-03-01 W4
ACTUAL | bar: 2017-11-01 W1
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-11-01 W2
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 W2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W1
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-10-16 W1
|  | 3.Tools & Measurement equipments |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
|  |  |  | A'Class tool design (broach,hob shaving Frazing cutter and honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
|  |  |  | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
[6 empty] | ACTUAL | 2018-01-01 W1: Packing for T1 trials; 2018-02-01 W2: Approval from Customer; 2018-03-01 W2: MP bin receive
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2 to 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-12-01 W4 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL | bar: 2017-10-16 W1
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL | bar: 2017-10-16 W1
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W3; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W1
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W3
ACTUAL
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4; 2018-02-01 W4 to 2018-03-01 W2
ACTUAL
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-11-01 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W1
ACTUAL
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | 2.Prevention |  | ①Design verification | NA | PLAN
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W4 to 2018-01-01 W5; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2018-03-01 W1 to 2018-03-01 W4
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W3 to 2018-02-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-03-01 W4 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W3 to 2018-03-01 W4
EVALUATION
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
For T1 & PL1
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Some technical issue yet to clarify from TVSM. Event progressis based on clarifications & closure.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
QCD-3
T0 Event Process
PL1 Event
200 NOS PER DAY
800 NOS PER DAY
T-0 Sample will be ready by DEC-1 WK

## MTP WEGO REV-2 (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [83 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [53 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [85 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-12-01 W2: T-0; 2018-02-01 W2: T1; 2018-03-01 W2: PL1; 2018-03-01 W4: MP
[89 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W2: 25; 2018-02-01 W2: 100; 2018-03-01 W2: 1000; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 200; 2018-04-01 W4: 400; 2018-05-01 W1: 600; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
ACTUAL
|  |  |  | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W4 to 2018-01-01 W1; 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | Sample Making | ME-BLR | PLAN | bar: 2017-10-16 W2 to 2017-12-01 W1; 2018-01-01 W4 to 2018-03-01 W4
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-02-01 W2; 2018-03-01 W2; 2018-03-01 W4
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-11-01 W2
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 W2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
|  |  |  | A'Class tool design (broach,hob shaving Frazing cutter and honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
|  |  |  | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
[6 empty] | ACTUAL | 2018-01-01 W1: Packing for T1 trials; 2018-02-01 W2: Approval from Customer; 2018-03-01 W2: MP bin receive
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2 to 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-12-01 W4 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W3; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W3
ACTUAL | bar: 2017-11-01 W2
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4; 2018-02-01 W4 to 2018-03-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-11-01 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W1
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  | 2.Prevention |  | ①Design verification | NA | PLAN
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W4 to 2018-01-01 W5; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2018-03-01 W1 to 2018-03-01 W4
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W3 to 2018-02-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-03-01 W4 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W3 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
For T1 & PL1
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Some technical issue yet to clarify from TVSM. Event progressis based on clarifications & closure.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
PL1 Event
200 NOS PER DAY
800 NOS PER DAY
T-0 Sample will be ready by DEC-2 WK
QCD-3

## MTP WEGO REV-3 27-11-2017 (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [49 empty] | 03 | 2017-11-27 |  |  | Preponement of mp from Mar-17 to Feb-17 | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [53 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [85 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-12-01 W1: T-0; 2018-02-01 W1: T1; 2018-02-01 W3: PL1; 2018-02-01 W4: MP
[89 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-02-01 W1: 100; 2018-02-01 W3: 1000; 2018-02-01 W4: 200; 2018-03-01 W1: 200; 2018-03-01 W2: 200; 2018-03-01 W3: 200; 2018-03-01 W4: 200; 2018-04-01 W1: 400; 2018-04-01 W2: 600; 2018-04-01 W3: 800; 2018-04-01 W4: 800; 2018-05-01 W1: 800; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[6 empty] | ACTUAL | 2017-12-01 W3: 5
|  |  |  | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | ME-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1; 2018-01-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3; 2018-01-01 W1
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2
|  |  |  | Sample Making | ME-BLR | PLAN | 2018-01-01 W2: WITH AUTOMATION TRIAL
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-12-01 W1
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-12-01 W1
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5; 2017-10-16 W4 to 2017-11-01 W5
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2018-02-01 W1: set up; 2018-02-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-12-01 W3; 2018-01-01 W1
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
|  |  |  | A'Class tool design (broach,hob shaving) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W3
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
|  |  |  | A'Class tool design ( honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
|  |  |  | A'Class tool design (Frazing cutter ) | PE-BWL | PLAN | 2018-04-01 W1: GROTOMAT m/c to be used for MP till frzaing cutters will come.
ACTUAL | bar: 2017-07-16 W3 to 2017-12-01 W3
|  |  |  | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | Jigs |  | HT jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W2
|  | 3a. Guages |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
ACTUAL | bar: 2017-08-16 W4 to 2017-10-16 W2; 2017-10-16 W4; 2017-12-01 W2 to 2017-12-01 W3
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-12-01 W1 to 2017-12-01 W3
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W5
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3; 2018-05-01 W5
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  | 2.Prevention |  | ①Design verification | NA | PLAN
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W5
|  |  |  | ③QA machine / Pokayoke verification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[6 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[6 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1
|  |  |  | ②Process capability study | Production,QA | PLAN
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W2 to 2018-02-01 W3
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-02-01 W4 to 2018-05-01 W5; 2018-07-01 W1 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W4 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2 to 2017-11-01 W4
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
Joint Insp. on 5th Dec
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Lead and Profile error tolerance not fixed for all WEGO parts, Tolerance to be agreed with customer.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
200 NOS PER DAY
800 NOS PER DAY
QCD-3
FOR MP
FOR MP
Drawing will be release on 8th/9th Dec
T1
PL1
Packing Approval
Bin Order for MP
MP BIN Receive
Joint inspection completed on 15-12-027
Rack rolling m/c received in 2WK of NOV-17
5 sets dispatched on 19-12-2017 ( sch not uploaded in TVS portal)

## MTP WEGO REV-3 31-01-2018 (hidden)
MASTER TIMING PLAN |  |  |  |  | Confirmation required on completion | ◎ | [49 empty] | 03 | 2017-11-27 |  |  | Preponement of mp from Mar-17 to Feb-17 | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | Cross Functional Team
[5 empty] | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [11 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [54 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE | [5 empty] | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[6 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[6 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [86 empty] | HT | Ganesh san
[6 empty] | WEGO |  | 2017-12-01 W1: T-0; 2018-02-01 W1: T1; 2018-02-01 W3: PL1; 2018-02-01 W4: MP
[90 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-02-01 W1: 100; 2018-02-01 W3: 300; 2018-02-01 W4: 200; 2018-03-01 W1: 200; 2018-03-01 W2: 200; 2018-03-01 W3: 200; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 400; 2018-04-01 W4: 600; 2018-05-01 W1: 800; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[7 empty] | ACTUAL | 2017-12-01 W3: 5
[5 empty] | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
[5 empty] | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Drawing Release from ME BLR to QA, Prod & Pur BLR | ME-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1; 2018-01-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3; 2018-01-01 W1
[5 empty] | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2; 2018-02-01 W1; 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2
[5 empty] | Sample Making | ME-BLR | PLAN | 2018-01-01 W2: WITH AUTOMATION TRIAL
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-12-01 W1
| New mechanism / New structure | Specifications/drawings |  |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[7 empty] | ACTUAL | 2017-03-16 W4: PO DONE
[5 empty] | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5; 2017-10-16 W4 to 2017-11-01 W5
[5 empty] | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
[5 empty] | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2018-02-01 W1: set up; 2018-02-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
[5 empty] | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
[5 empty] | A'Class tool design (broach,hob shaving) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W3
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design ( honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design (Frazing cutter ) | PE-BWL | PLAN | 2018-04-01 W1: GROTOMAT m/c to be used for MP till frzaing cutters will come.
ACTUAL | bar: 2017-07-16 W3 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
[5 empty] | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4
|  | Jigs |  |  | HT jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
|  | 3a. Guages |  |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4
|  | 4.Logistics |  |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
ACTUAL | bar: 2017-08-16 W4 to 2017-10-16 W2; 2017-10-16 W4; 2017-12-01 W2 to 2017-12-01 W3
|  | 5.Documentations |  |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
[5 empty] | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W4
[5 empty] | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
[5 empty] | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-12-01 W1 to 2017-12-01 W3
[5 empty] | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | 6.Operator training |  |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | Progress of the P-FMEA |  |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W4
|  | Process design review |  |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W4
| Capacity | Production capacity |  |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
| Quality | Quality concept |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
|  | Issues with changing point |  |  |  | QA-BLR | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | Quality managemant plan |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3; 2018-05-01 W5
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1
[5 empty] | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
|  | 2.Prevention |  |  | ①Design verification | NA | PLAN
ACTUAL
[5 empty] | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W5
[5 empty] | ③QA machine / Pokayoke verification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W4
[5 empty] | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 3.Evaluation of product |  |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
[5 empty] | ②Process capability study | Production,QA | PLAN
ACTUAL
[5 empty] | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W2 to 2018-02-01 W3
ACTUAL
|  | 4.Process verification |  |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 5.Supplier control |  |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
[5 empty] | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
|  | 6.Initial process flow control |  |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-02-01 W4 to 2018-05-01 W5; 2018-07-01 W1 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W4 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
As per Bhaskar San Frazing cutter is receiving on 3rd WK of March
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
Joint Insp. on 5th Dec
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Lead and Profile error tolerance not fixed for all WEGO parts, Tolerance to be agreed with customer.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
200 NOS PER DAY
800 NOS PER DAY
QCD-3
FOR MP
FOR MP
Drawing will be release on 8th/9th Dec
T1
PL1
Packing Approval
Bin Order for MP
MP BIN Receive
Joint inspection completed on 15-12-17
Rack rolling m/c received in 2WK of NOV-17
5 sets dispatched on 19-12-2017 ( sch not uploaded in TVS portal)
Frazing cutter receiving on 31-03-2018
MP Starts from 26-02-2018
Upto 2nd WK of April 200 Sets can be dispatch to TVSM as per Grotomat machine capacity
Frazing sample making and Submission

## Sheet1 (hidden)
| TVS Project Projects | [5 empty] | DATE: |  | 18th Jan
Sl No | Project & Event | PART | Present Status | Action | Resp. | Target date | Status | Dispatch Date | Remarks
1 | TVS - WEGO - T1 EVENT | GEAR REAR WHEEL | Shaving Completed | 9 point study part insp to be done before HT & HT to be done | Prashanth san & ganesh San | 2018-01-18
|  | GEAR INTERMEDIATE | Receiving insp completed | Turning, broaching hobbing & shaving to be done | ME/QA/PROD | 18 & 19-01-2018
|  | SHAFT REAR WHEEL | Bhagwan supplier parts received & found ok | Puncharatna supplier parts found NG, New sozai required | PUR | 2018-01-18 | ∆
|  | SHFAT INTERMEDIATE | Spline rolling completed | Hobbing & shaving to be done | ME/QA/PROD | 2018-01-18
|  | SHAFT CLUTCH | Spline & thread rolling completed | Shaving to be done | ME/QA/PROD | 2018-01-19
2 | TVS - WEGO - PL EVENT |  | Sozai Ordered for PL Event | Sozai to be receiving | Prahalad San |  | ∆

## Concerned points (hidden)
WEGO MP preponement from 4th WK of Mar to 4th WK of Feb-18 concerned points
SL No |  | Problem Points | Counter measure / Action Plan | Resp | Target date
1 | Drawings | Lead and Profile error tolerance not fixed for all WEGO parts | Tolerance to be agreed with customer. | BWL-PE
2 | Sozai | Sozai lead time is 1 month, If approval given after T1 event MP will delay | So TVSM need to provide go ahead for MP sozai drawing during To joint insp. Time | Sales
3 | Toolings | Frazing cutter lead time is 20 WK, so MAP-ID reach time Mar last wk 2018 (for Gear intermediate and Gear Rear Wheel parts | GROTOMAT m/c to be used for MP with customer approval till frzaing cutters will come. | Sales
4 | HT Jigs | HT jigs lead time is 3.5 months, MAP-ID reach time is Mar-18 for all parts | Min order qty to be air freighted to reduce lead time by 1 month | ME / Pur
5 | Fixture | Eddy current fixture not available | M/c or Fixure to be arranged from MSI or Local | ME / Pur
6 | M/C | Auto GRT M/c delay in delivery | Need to monitor closely and Speed up the activity | Purchase

## Existing condition status (hidden)
Customer approved for existing condition
1 | PRESENT STATUS | PRESENT STATUS HT COMPLETED | THREAD ANNEALING | LASER MARKING | AXIS GRINDING | LAYOUT INSPECTION | ASSEMBLY | FINAL INSPECTION | HOD'S INSP | Ready for Dispatch
| Shaft rear wheel |  | 2018-02-08 | 2018-02-09 | 10-02-2018 TO 12-02-2018 | 13-02-2018 & 14-02-2018 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-19
2 | PRESENT STATUS | PRESENT STATUS HT COMPLETED | THREAD ANNEALING | STRAIGHTENING | LASER MARKING | AXIS GRINDING | LAYOUT INSPECTION | FINAL INSPECTION
| Shaft Clutch |  | 2018-02-09 | 2018-02-10 | 2018-02-10 | 2018-02-13 | 14-02-2018 & 15-02-2018 | 2018-02-15
3 | PRESENT STATUS | PRESENT STATUS HONNIG COMPLETED | - | - | - | LAYOUT INSPECTION | ASSEMBLY | FINAL INSPECTION
| Gear Rear wheel |  | - | - | - | 2018-02-08 | 2018-02-15 | 2018-02-16
4 | PRESENT STATUS | PRESENT STATUS HT COMPLETED | - | - | - | LASER MARKING | LAYOUT INSPECTION | FINAL INSPECTION
| Gera Intermediate |  | - | - | - | 2018-02-09 | 2018-02-10 | 2018-02-12
5 | PRESENT STATUS | LAYOUT INSPECTION FOUND OK | - | - | - | - | - | FINAL INSPECTION
| Shaft Intermediate |  | - | - | - | - | - | 2018-02-08
SL No | Points |  |  |  | Target | No of days
1 | Customer Approved for Existing condition |  |  |  | 2018-02-07
2 | T-1 parts ready for dispatch - 100 sets |  |  |  | 2018-02-19 | 12
3 | PL parts ready for dispatch 300 Sets |  |  |  | 2018-03-05 | 14
4 | MP Starts from |  |  |  | 2018-03-16 | 10

## MTP WEGO REV-3 Exist cond (hidden)
MASTER TIMING PLAN |  |  |  |  | Confirmation required on completion | ◎ | [49 empty] | 03 | 2017-11-27 |  |  | Preponement of mp from Mar-17 to Feb-17 | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | Cross Functional Team
[5 empty] | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [11 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [54 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE | [5 empty] | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[6 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[6 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [86 empty] | HT | Ganesh san
[6 empty] | WEGO |  | 2017-12-01 W1: T-0; 2018-02-01 W3: T-1; 2018-03-01 W1: PL1; 2018-03-01 W3: MP
[90 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-02-01 W3: 100; 2018-03-01 W1: 300; 2018-03-01 W3: 200; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 400; 2018-04-01 W4: 600; 2018-05-01 W1: 800; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[7 empty] | ACTUAL | 2017-12-01 W3: 5
[5 empty] | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
[5 empty] | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Drawing Release from ME BLR to QA, Prod & Pur BLR | ME-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1; 2018-01-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3; 2018-01-01 W1
[5 empty] | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2; 2018-02-01 W1; 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2; 2018-02-01 W1
[5 empty] | Sample Making | ME-BLR | PLAN | 2018-01-01 W2: WITH AUTOMATION TRIAL
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-01-01 W5; 2018-02-01 W4; 2018-03-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-01-01 W5
| New mechanism / New structure | Specifications/drawings |  |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[7 empty] | ACTUAL | 2017-03-16 W4: PO DONE
[5 empty] | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5; 2017-10-16 W4 to 2017-11-01 W5
[5 empty] | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
[5 empty] | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2018-03-01 W1: set up; 2018-03-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
[5 empty] | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
[5 empty] | A'Class tool design (broach,hob shaving) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W3
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design ( honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design (Frazing cutter ) | PE-BWL | PLAN | 2018-04-01 W1: GROTOMAT m/c to be used for MP till frzaing cutters will come.
ACTUAL | bar: 2017-07-16 W3 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
[5 empty] | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W1
|  | Jigs |  |  | HT jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
|  | 3a. Guages |  |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W1
|  | 4.Logistics |  |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
ACTUAL | bar: 2017-08-16 W4 to 2017-10-16 W2; 2017-10-16 W4; 2017-12-01 W2 to 2017-12-01 W3
|  | 5.Documentations |  |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
[5 empty] | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5
[5 empty] | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
[5 empty] | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-12-01 W1 to 2017-12-01 W3
[5 empty] | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
[5 empty] | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | 6.Operator training |  |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | Progress of the P-FMEA |  |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
|  | Process design review |  |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
| Capacity | Production capacity |  |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
| Quality | Quality concept |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
|  | Issues with changing point |  |  |  | QA-BLR | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W5
|  | Quality managemant plan |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3; 2018-05-01 W5
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1
[5 empty] | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W1
[5 empty] | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W1
|  | 2.Prevention |  |  | ①Design verification | NA | PLAN
ACTUAL
[5 empty] | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5
[5 empty] | ③QA machine / Pokayoke verification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5
[5 empty] | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 3.Evaluation of product |  |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
[5 empty] | ②Process capability study | Production,QA | PLAN
ACTUAL
[5 empty] | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W2 to 2018-02-01 W3
ACTUAL
|  | 4.Process verification |  |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 5.Supplier control |  |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
[5 empty] | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
|  | 6.Initial process flow control |  |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-02-01 W4 to 2018-05-01 W5; 2018-07-01 W1 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W4 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
As per Bhaskar San Frazing cutter is receiving on 3rd WK of March
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
Joint Insp. on 5th Dec
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Lead and Profile error tolerance not fixed for all WEGO parts, Tolerance to be agreed with customer.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
200 NOS PER DAY
800 NOS PER DAY
QCD-3
FOR MP
FOR MP
Drawing will be release on 8th/9th Dec
T1
PL1
Packing Approval
Bin Order for MP
MP BIN Receive
Joint inspection completed on 15-12-17
Rack rolling m/c received in 2WK of NOV-17
5 sets dispatched on 19-12-2017 ( sch not uploaded in TVS portal)
Frazing cutter receiving on 31-03-2018
MP Starts from 16-03-2018
Upto 2nd WK of April 200 Sets can be dispatch to TVSM as per Grotomat machine capacity
Frazing sample making and Submission
ON 19-02-18
ON 05-03-18

## C1
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR C1 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | C1 | JIG / FIXTURE | T0/PP0 | HOBBING | HOB CUTTER TOUCH TO FIXTURE BOTTOM BASE. (Fixture base commonise) |  | Ø62.8 -0.1 MM | Ø67.0 MM | BOTTOM BASE COMMON PLANED. | 図面未確認 | FIXTURE BASE MODIFIED AS PER COMMONISATION. | AVAILABLE SPARE FIXTURE TO BE MODIFY AS PER NEW DESIGN. | AMBIKA | 29.11.18 | COMPLETED
2 | C1 | JIG / FIXTURE | T0/PP0 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.06 MM | 0.03~0.08 MM | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
3 | C1 | JIG / FIXTURE | PP0/PP1 | HOBBING | HOBBING PCD MORE, DUE TO LOCATOR UNDERSIZE. (LOCATOR COMMONISED) |  | 0.04 MM | 0.056 MM | PART LOCATING DIAMETER UNDERSIZE BY 0.008MM. PART LOCATOR COMMONISED. | 部品内径規格は？それぞれ | NEW LOCATOR MADE IN TOOL ROOM. | NEW LOCATOR TO BE ARRANGED. | AMBIKA | 20.02.19 | COMPLETED
4 | C1 | SOZAI | PP1 | RECEVING INSPECTION | STEP IN KIDNEY OBSERVED IN AMTEK SUPPLIED PARTS (ALL PARTS) |  | 0.12 WRT E, D 35.2 ± 0.1 | 0.01 ~ 0.04 35.232 | POSITION CHECKED ONLY BY CMM WITH TAKING POINTS IN KIDNEY RADIUS, NOT ON THE LAND | ピアス？加工？確認頻度、工程能力？ | SEGREGATTION AND REWORK DONE TO REMOVE STEP | SUPPLIER END KIDNEY INSPECTION TO BE ENSURED 100%. | PANKAJ SAN
5 | C1 | METHOD | PP1 | HT | ひずみ |  |  |  | 9点3サイクルしていない。 | 9点3サイクルしていない。 | なし | 9点3サイクル

## C2
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR C2 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | C2 | JIG / FIXTURE | PP0/PP1 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.06 | 0.03~0.08 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
2 | C2 | TOOL | PP0/PP1 | HOBBING | LEAD&PROFILE IS NG ( FF NG) | 4 | ALL TEETH LEAD & PROFILE GRAPH NG FF-22 FQ- 18 | CUSTOMER REQUIREMENT IS ALL TEETH GRAPH (4 TEETH GRAPH CAN BE MAKE IT OK) FF- 13.1 (OK) FQ- 27.8 (NG) | HOB LEAD ANGLE DESIGN ISSUE (4S HOB DESIGNED). |  | GEAR M2 (2S) HOB IS USED (COMMON DESIGNED HOB). | HOB DESIGN TO BE CHECK & TRIAL TO BE ARRANGE. | MAKER / NARENDRA | 10.04.19 | UNDER PROGRESS.
3 | C2 | JIG / FIXTURE | PP0/PP1 | HOBBING | HOBBING PCD MORE, DUE TO LOCATOR UNDERSIZE. (LOCATOR COMMONISED) |  | 0.04 | 0.062 | PART LOCATING DIAMETER UNDERSIZE BY 0.012MM. PART LOCATOR COMMONISED. | 部品内径規格は？それぞれ | NEW LOCATOR MADE IN TOOL ROOM. | NEW LOCATOR TO BE ARRANGED. | AMBIKA | 20.02.19 | COMPLETED
4 | C2 | METHOD | PP1 | HOBBING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD- 61.900~ 61.930 SPAN-(21.556 ) | 61.909 / 61.920 21.554 / 21. 556 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 23.02.19 | UNDER PROGRESS.
5 | C2 | INSPECTION | PP1 | LAYOUT | ALL TEETH GRAPH | 4 | ALL TEETH LEAD & PROFILE GRAPH NG FF-22 FQ- 18 | CUSTOMER REQUIREMENT IS ALL TEETH GRAPH (4 TEETH GRAPH CAN BE MAKE IT OK) FF- 13.1 (OK) FQ- 27.8 (NG) | HOB LEAD ANGLE DESIGN ISSUE (4S HOB DESIGNED). |  | GEAR M2 (2S) HOB IS USED (COMMON DESIGNED HOB). | HOB DESIGN TO BE CHECK & TRIAL TO BE ARRANGE. | MAKER / NARENDRA | 10.04.19 | UNDER PROGRESS.

## C3
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR C3 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | C3 | METHOD | T0/PP0 | FORGING | KIDNEY RADIUS ONE SIDE FOUND NG | 77 | C/R 0.8~1.5 | 0.72/0.69 (RE-CHECK) | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED | SOMANATH | 10.02.19 | COMPLETED
2 | C3 | METHOD | PP0/PP1 | HOBBING | LEAD&PROFILE IS NG | 3 | FF-20 FQ-17 | FF- 23.4 FQ- 19.9 | HOB LEAD ANGLE DESIGN ISSUE (4S HOB DESIGNED). |  | GEAR M2 (2S) HOB IS USED (COMMON DESIGNED HOB). | HOB DESIGN TO BE CHECK & TRIAL TO BE ARRANGE. | MAKER / NARENDRA | 10.04.19 | UNDER PROGRESS.
3 | C3 | JIG / FIXTURE | T0/PP0 | HOBBING | HOB CUTTER TOUCH TO FIXTURE BOTTOM BASE. (Fixture base commonise) |  |  |  | BOTTOM BASE COMMON PLANED. | 図面未確認 | FIXTURE BASE MODIFIED AS PER COMMONISATION. | AVAILABLE SPARE FIXTURE TO BE MODIFY AS PER NEW DESIGN. | AMBIKA | 29.11.18 | COMPLETED
4 | C3 | JIG / FIXTURE | PP0/PP1 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.06 | 0.03~0.08 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
5 | C3 | FORGING | PP1 | FORGING | COUNTER DIA UNDERFILL PROBLEM | APPEARANCE | NO UNDERFILL | UNDER FILL AT 2 PLACES | FORGING PROCESS SETTING PARAMETER NG ( LOAD 180 & TEMP 1180). |  | SETTING PROCESS PARAMETER CHANGED (PRESS LOAD INCREASED 180 TO 200 , BILLET TEMP CHANGE FROM 1180~1200 TO 1220 ºC ) | PROCESS SETTING PARAMETERS STANDERDISE & DIE DESIGN TO BE REVIEW & FREEZED. | SOMANATH | 10.02.19 | COMPLETED
6 | [5 empty] | 37 | Depth 1.2±0.3 | 0.87/1.11
7 | [5 empty] | 58 | ø27+0.5 | 27.52
8 | C3 | METHOD | PP1 | TURNING-2 | BURR OBSERVED ON KIDNEY TURNED WALLS AND CHAMFER. | 89 | APPEARANCE | BURR OBSERVED IN KIDNEY SIDE HOLES | ROUGH TO FINISH STOCK NOT BALANCED. | 仕上げ取り代はいくつ？確認してください。 | REWORK DONE TO REMOVE BURR. | ROUGH TO FINISH STOCK BALANCE & TRIAL TO BE DONE FOR BURR ELIMINATION, & PROGRAM TO BE FREEZE. | MAHESH/MANOHAR/PRAMOD | 06.04.19 | UNDER PROGRESS.
9 | C3 | METHOD | PP1 | HOBBING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD- 54.150 ~ 54.180 SPAN-(21.545) | 54.152 21.541 | PARTS SEGREGATED & OFFRED FOR INSPECTION | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 06.04.20 | UNDER PROGRESS.
10 | C3 | METHOD | PP1 | HOBBING | DEBURRING TOOL MARK OBSERVED ON PART |  | APPEARANCE | VISUAL NG | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | CFT | 02.04.19 | UNDER PROGRESS.
11 | C3 | ＨＦ | PP1 | ＨＦ | 内径確認不可能 |  |  |  | 作業基準表NG | 作業基準表NG |  | 基準書見直し要
12 | C3 | INSPECTION | PP1 | TURNING-2 | BURR OBSERVED IN KIDNEY SIDE HOLES | 89 | APPEARANCE | BURR OBSERVED IN KIDNEY SIDE HOLES | PROCESS STAGE BURR LIMIT JUDGEMENT STUDY REQUIRED. |  | AHTER HT MANUALY DEBURR & SHOT BLAST | SOFT STAGE BURR LIMIT TO BE DEFINE & JUDGEMENT SAMPLE TO BE MADE. BURR DIMENSIONAL LIMIT ADD IN PROCESS SHEET. | PRASHANTH / GANESH | 15.04.19 | UNDER PROGRESS.
13
14 | C3 | INSPECTION | T0 | LAYOUT | C 0.5+0.2 NG | 24 | C 0.5+0.2 | 0.19~0.2 | PROCESS SHEET WRONG DEFINED C0.3 MANTIONED AGAINST C0.5 |  | PROCESS SHEET UPDATED & SAME CHANGE IN TURNING PROGRAM | PROCESS SHEET VERIFIED WITH FINAL DRAWING BY COLOUR MATCHING SYSTEM | ASHOK | 10.01.19 | COMPLETED
15 | C3 | INSPECTION | PP0 | LAYOUT | Depth 1.2±0.3 | 37 | Depth 1.2±0.3 | 0.87/1.11 | FORGING PROCESS SETTING PARAMETER NG ( LOAD 180 & TEMP 1180). |  | SETTING PROCESS PARAMETER CHANGED (PRESS LOAD INCREASED 180 TO 200 , BILLET TEMP CHANGE FROM 1180~1200 TO 1220 ºC ) | PROCESS SETTING PARAMETERS STANDERDISE & DIE DESIGN TO BE REVIEW & FREEZED. | SOMANATH | 10.02.19 | COMPLETED

## C4
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR C4 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | C4 | TOOL | T0/PP0 | TURNING-1 | IDENTIFICATION NOT POSSIBLE WITH WNMG INSERT TOOL |  | DEPTH 0.1~0.3, WIDTH 2~2.5 | FORM NOT OK | EXISTING TOOL TOUCH TO OD WHLIE GROOV MAKING. |  | DNMG INSRT & TOOL NEED TO ADD FOR FACE, OD & IDENTIFICATION GROOVE. | DNMG TOOL ADD IN TOOL LIST/PROCESS SHEET. | MAHESH RAO, PRAMOD | 10.01.19 | COMPLETED
2 | C4 | JIG / FIXTURE | T0/PP0 | TURNING-2 | JAWS RADIUS TOUCH TO STOPPER, SO MOUNTING NOT POSSIBLE |  | STRAIGHT FORM | RADIUS FORM | MACHINE MAKER/MAP DRAWING NOT MATCH WITH ACTUAL PART. |  | JAWS REWORKED FROM RADIUS TO STRAIGHT IN TOOL ROOM | JAWS DRAWING REVISED FROM RADIUS TO STRAIGHT FORM IN DRAWING & CONTROL COPY RECORDED. (EXISTING DRAWING OBSOLETE DONE). | MAHESH | 05.01.19 | COMPLETED
3 | C4 | JIG / FIXTURE | T0/PP0 | HOBBING | HOBBING BOTTOM LOCATOR LOCATING DEPTH UNDERSIZE BY 2.0MM |  | 15.5 MM (13.5 EXISTING DRAWING) | 13.5 MM | BASE DRAWING WAS NOT MATCH WITH ACTUAL PART. |  | LOCATOR DEPTH REWORKED BY 2.0MM IN TOOL ROOM | LOCATOR LOCATING DEPTH REVISED FROM 13.5 TO 15.5MM IN DRAWING & CONTROL COPY RECORDED. (EXISTING DRAWING OBSOLETE DONE). | MAHESH P | 05.01.19 | COMPLETED
4 | C4 | JIG / FIXTURE | T0/PP0 | SHAVING | SHAVING HOLDER PART NOT LOCATING PROPERLY. LOCATOR WIDTH IS NG BY 0.6 MM. |  | 55 -0.1/-0.2 MM | 55.6 MM | HOLDER WIDTH WAS MORE THAN SPEC (MORE BY 0.6MM, GRINDING NOT DONE) |  | LOCATOR REWORK (0.6MM UNDERSIZE BY 0.6MM) DONE IN TOOL ROOM | NEW HOLDER ARRANGED FROM SUPPLIER (AS PER DRAWING). | ARUN | 15.02.19 | COMPLETED
5 | C4 | JIG / FIXTURE | PP1 | HOBBING | PCD RUNOUT IS MORE |  | 0.03 MAX | 0.04 ~0.055 | TAILSTOCK RUNOUT NG (COMMON TAILSTOCK) | Ｋ０NA用の冶具があるのか？ | TAILSTOCK ARBOR LOCATING FACE GRINDING DONE | SPARE TAILSTOCK TO BE CHECK AS PER DRAWING. | HUBLI | 03.04.19 | UNDER PROGRESS.
6 | C4 | METHOD | PP0 | FINAL STAGE (HOBBING) | DEBURRING BURR OBSERVED ON PART TEETH END. |  | 0.1 MM | VISUALLY OBSERVED NOT MEASURED. | PROCESS CONSTRAINT. | デバ高さ設定、規格の標準なし | BURR REWORKED. | 1) HOBBING LOADING PATTERN TO BE CHANGE & DO DEBURRING ONLINE. 2) SHOT BLASTING LOADING PATTERN CHANGE & PROCESS TO BE VALIDATE. | GANESH / ASHOK | 10.04.19 | UNDER PROGRESS.
7 | C4 | METHOD | PP1 | SHAVING | SHAVING SPAN VARIATION OBSERVED |  | 0.030 MAX | 0.015 ~ 0.040 | HOBBING PCD RUNOUT IMPACT | ホブの管理ができていない。 | PARTS ARE SEGEGATED WITH FOR SPAN (WITHIN SPEC) & OFFERED FOR EVENT. | 1) SPAN TO OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | BWL- PE MAHESH RAO | 28.03.19 | UNDER PROGRESS.
8 | C4 | METHOD | PP1 | HOBBING&SHAVING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD-50.440~ 50.480 SPAN - (15.730) | 50.510 (NG) 15.735 (OK) | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 28.03.20 | UNDER PROGRESS.
9 | C4 | METHOD | PP0 | SHAVING | Lead & profile | 7 | Lead & profile FFT - 5 ~ 15 | fft | SHAVING CUTTER RESHARPENING NOT OK |  | SHAVING CUTTER CORRECTED AS PER FFT 9POINT DISTORTION STUDY | RESHARPENING PROGRAM FREEZED & CONTROLLED FOR FUTURE RESHARPENING | HARISH | 20.01.19 | COMPLETED

## C5
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR C5 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | C5 | TOOL | T0/PP0 | TURNING-1 | IDENTIFICATION NOT POSSIBLE WITH WNMG INSERT TOOL |  | DEPTH 0.1~0.3, WIDTH 2~2.5 | FORM NOT OK | EXISTING TOOL TOUCH TO OD WHLIE GROOV MAKING. |  | DNMG INSRT & TOOL NEED TO ADD FOR FACE, OD & IDENTIFICATION GROOVE. | DNMG TOOL ADD IN TOOL LIST/PROCESS SHEET. | MAHESH RAO, PRAMOD | 10.01.19 | COMPLETED
2 | C5 | JIG / FIXTURE | T0/PP0 | TURNING-2 | JAWS RADIUS TOUCH TO STOPPER, SO MOUNTING NOT POSSIBLE |  | STRAIGHT FORM | RADIUS FORM | MACHINE MAKER/MAP DRAWING NOT MATCH WITH ACTUAL PART. |  | JAWS REWORKED FROM RADIUS TO STRAIGHT IN TOOL ROOM | JAWS DRAWING REVISED FROM RADIUS TO STRAIGHT FORM IN DRAWING & CONTROL COPY RECORDED. (EXISTING DRAWING OBSOLETE DONE). | MAHESH | 05.01.19 | COMPLETED
3 | C5 | JIG / FIXTURE | T0/PP0 | SHAVING | SHAVING HOLDER PART NOT LOCATING PROPERLY. LOCATOR WIDTH IS NG BY 0.6 MM. |  | 55 -0.1/-0.2 MM | 55.6 MM | HOLDER WIDTH WAS MORE THAN SPEC (MORE BY 0.6MM, GRINDING NOT DONE) |  | LOCATOR REWORK (0.6MM UNDERSIZE BY 0.6MM) DONE IN TOOL ROOM | NEW HOLDER ARRANGED FROM SUPPLIER (AS PER DRAWING). | ARUN | 15.02.19 | COMPLETED
4 | C5 | METHOD | T0/PP0 | FORGING | ID CHAMFER DIAMETER & ANGLE IS NG |  | Ø 26 +0.3 120⁰ ± 1°30' | ANGLE MATERIAL UNEVEN | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED | SOMANATH | 10.02.19 | COMPLETED
5 | C5 | TOOL | T0/PP0/PP1 | BROACHING | BROACH CUTTER IS LENGTH IS MORE |  | 700 MM | 800MM | MACHINE CONSTRAINT |  | LENGTH ADJUSTED IN PROGRAMME&MACHINE HELP OF MAINTANACE DEPT | NEW MACHINE PROCUREMENT, BROACH LENGTH FEASIBILITY TO BE CHECK. | BHASKAR | 21.01.19 | COMPLETED
6 | C5 | METHOD | PP1 | HOBBING | DEBURRING BURR OBSERVED ON PART |  | 0.1 MM | VISUALLY OBSERVED NOT MEASURED. | PROCESS CONSTRAINT. | デバ高さ設定、規格の標準なし | BURR REWORKED. | HOBBING LOADING PATTERN TO BE CHANGE & GROOVE DIAMETER REDUCE (Ø38 TO Ø37MM) BY SPEC CHANGE FROM HMSI. | BWL- PE MAHESH RAO | 20.04.19 | UNDER PROGRESS.
7 | C5 | METHOD | PP1 | SHAVING | SHAVING SPAN VARIATION OBSERVED |  | 0.027 MAX | 0.015~0.040 | HOBBING PCD RUNOUT IMPACT | ホブの管理ができていない。 | PARTS ARE SEGEGATED WITH FOR SPAN (WITHIN SPEC) & OFFERED FOR EVENT. | 1) SPAN TO OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | BWL- PE | 28.03.19 | UNDER PROGRESS.
8 | C5 | METHOD | PP1 | HOBBING&SHAVING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD - 48.680 ~ 48.710 SPAN -(16.635 ) | 48.690 16.625 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 24.02.19 | UNDER PROGRESS.
9 | C5 | METHOD | PP1 | TURNING 2 | 長手確認がかっこ寸法 |  |  |  | 作業基準表NG | 作業基準表NG |  | 基準書見直し要
10 | C5 | INSPECTION | PP1 | LAYOUT | SPAN 16.676 -0.026 / -0.053 | 5 | SPAN 16.676 -0.026 / -0.053 | . -0.018 MAX / -0.032 MIN | HOBBING PCD RUNOUT IMPACT |  | PARTS ARE SEGEGATED WITH FOR SPAN (WITHIN SPEC) & OFFERED FOR EVENT. | 1) SPAN TO OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | BWL- PE | 28.03.19 | UNDER PROGRESS.

## M2
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR M2 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | M2 | TOOL | T0/PP0 | HOBBING | DEBURRING TOOL MARK OBSERVED ON PART |  | APPEARANCE | VISUAL NG | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | 1) DEBURRING TOOL SETUP CORRECTED. 2) DEBURRING TOOL FLAT GRINDING (0.3MM FLAT) | 1) DEBURRING TOOL SETTING SOP TO BE PREPARE. 2) DEBURRING TOOL RESHARPENING AS PER DRAWING (0.3 MM FLAT GRINDING NOT DONE) 2) DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | 1) HUBALI 2) HARISH 3) NARENDRA | 02.04.19 | UNDER PROGRESS.
2 | M2 | METHOD | PP1 | HOBBING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD - 34.760~ 34.790 SPAN - (15.679) |  | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 02.04.19 | UNDER PROGRESS.
3 | M2 | INSPECTION | PP1 | LAYOUT | SPLINE CHAMFER DENT OBSERVED | 33 | APPEARANCE no dent | SPLINE CHAMFER DENT OBSERVED | HOBBING MANUALY PROCESSED ( ARBOR TOUCH MARK) |  | PARTS SEGGRIGATEED & HANDOVER FOR EVENT | AUTOMATION PROVEOUT & ENSURE DENT FREE PARTS. | MAHESH | 25.03.19 | UNDER PROGRESS.
4 | M2 | INSPECTION | PP0 | LAYOUT | Apperarence | 33 | Apperarence | Deburring cutter mark | DEBURRING TOOL SETTING NG. |  | 1) DEBURRING TOOL SETUP CORRECTED. 2) DEBURRING TOOL FLAT GRINDING (0.3MM FLAT) | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | CFT | 02.04.19 | UNDER PROGRESS.

## M3
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR M3 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/ Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | M3 | METHOD | T0/PP0 | FORGING | FORGING SCALE NOT CLEAN IN SHOT BLASTING. |  | APPEARANCE (0.1MM SPEC) | VISUAL NG | SHOT BLASTING PROCESS TIME NOT VALIDATE |  | RE-SHOT BLASTING DONE | SHOT BLASTING PROCESS TIME & VOLUME TO BE VALIDATE | SOMANATH | 10.04.19
2 | M3 | METHOD | T0/PP0 | FORGING | RADIUS NG (R2) |  | R2 ±0.5 | 1.26 / 0.98 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED | SOMANATH | 10.02.19 | COMPLETED
3 | M3 | TOOL | T0/PP0 | TURNING-2 (LEFT&RIGHT HEAD) | IDENTIFICATION NOT POSSIBLE WITH WNMG INSERT TOOL |  | DEPTH 0.1~0.3, WIDTH 2~2.5 | FORM NOT OK | EXISTING TOOL TOUCH TO OD WHLIE GROOVE MAKING. |  | DNMG INSRT & TOOL NEED TO ADD FOR FACE, OD & IDENTIFICATION GROOVE. | DNMG TOOL ADD IN TOOL LIST/PROCESS SHEET. | MAHESH RAO, PRAMOD | 10.01.19 | COMPLETED
4 | M3 | METHOD | T0/PP0 | FORGING | TURNING ID CHAMFER NG |  | Ø18.6 ±0.3 (BOTH SIDES) | Ø18.12~19.1 | FORGING HEIGHT VARIATION |  | TURNING PROGRAMMED WITH DIA 18.6 & FACE CUT, TO CONTROL DIA 18.6. | CHAMFER DIAMETER AS A REFERENCE MENTION IN DRAWING, SPEC CHANGE REQUEST TO HMSI | CFT | 16.04.19 | UNDER PROGRESS
5 | M3 | TOOL | T0/PP0 | SHAPING | GRAPH LEAD ONE TEETH FOUND NG |  | FF- 20 MAX FQ- 17 MAX | FF- 23.5 FQ- 19.9 | ANALYSIS UNDER PROGRESS |  | FEED RATE IS CORRECTED IN PART PROGRAMME FOR TRIALS | 1) SHAPING CUTTER TRIAL ON DIFFERENT MACHINE & CHECK THE RESULT. 2) CUTTER DESIGN TO BE CHECK & REPAIR. | MAKER / NARENDRA | 30.03.19 05.04.19 | UNDER PROGRESS
6 | M3 | JIG / FIXTURE | PP1 | TURNING-2 | DENT MARK OBSERVED ON PART OD |  | APPEARANCE | VISUAL NG | JAWS DAMAGED (COMMONISE WITH RUNNING MODEL) | 爪の外径設定NG | OD MARK BUFFING DONE | NEW JAWS TO BE ARRANGE (SPARE MIN. STOCK MAINTAIN). | HUBALI | 30.03.19
7 | M3 | METHOD | PP1 | SHAPING | DEBURRING BURR OBSERVED ON PART |  | APPEARANCE (0.1MM SPEC) | VISUAL NG | DEBURRING TOOL SETTING NG. PROCESS CONSTRAING (FORGING HEIGHT VARIATION) | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | BWL- PE |  | UNDER PROGRESS.
8 | M3 | METHOD | PP1 | SHAPING | SPAN OR OBD CONFIRMATION |  | OBD - 42.605~42.635 SPAN- (15.685) | 42.618 NOT CHECKED | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE |  | UNDER PROGRESS.
9 | M3 |  |  | TURNING | 凸ダボ面取り表記なし |  |  |  |  | 作業基準表NG |  | 作業基準表改定
10 | M3 | INSPECTION | PP1 | LAYOUT | LEAD & PROFILE NG | 4 | LEAD & PROFILE NG (FF-20 FQ-17) | FF - 21.6 FQ - 18.9 | ANALYSIS UNDER PROGRESS |  | FEED RATE IS CORRECTED IN PART PROGRAMME FOR TRIALS | 1) SHAPING CUTTER TRIAL ON DIFFERENT MACHINE & CHECK THE RESULT. 2) CUTTER DESIGN TO BE CHECK & REPAIR. | MAKER / NARENDRA | 30.03.19 05.04.19 | UNDER PROGRESS
11 | M3 | INSPECTION | PP1 | LAYOUT | KIDNEY SIDE BURR | 118 | APPEARANCE | KIDNEY SIDE BURR | ROUGH TO FINISH STOCK NOT BALANCED. | 仕上げ取り代はいくつ？確認してください。 | REWORK DONE TO REMOVE BURR. | ROUGH TO FINISH STOCK BALANCE & TRIAL TO BE DONE FOR BURR ELIMINATION, & PROGRAM TO BE FREEZE. | MAHESH/MANOHAR/PRAMOD | 06.04.19 | UNDER PROGRESS.
12 | M3 | INSPECTION | PP0 | LAYOUT | Rz 12.5 | 33 | Rz 12.5 | 9.415/19.299 | TURNING CUTTING PARAMETER NOT OK (RPM- 1800, FEED-0.12) |  | CUTTING PARAMETER CHANGE TO 2500 RPM & 0.08 FEED RATE. & SURFACE ACHIEVED BELOW Rz6.0 | PROGRAM TO BE FINALISE & CONTROLLED. | MAHESH | 15.02.19 | COMPLETED
13 | M3 | INSPECTION | PP0 | LAYOUT | CHAMFER ø18.6+0.3 | 42 | CHAMFER ø18.6+0.3 | 18.07- KIDNEY SIDE 18.69-LUG SIDE (OK) | FORGING HEIGHT VARIATION |  | TURNING PROGRAMMED WITH DIA 18.6 & FACE CUT, TO CONTROL DIA 18.6. | CHAMFER DIAMETER AS A REFERENCE MENTION IN DRAWING, SPEC CHANGE REQUEST TO HMSI | CFT | 16.04.19 | UNDER PROGRESS
14 | M3 | INSPECTION | PP0 | LAYOUT | Rz25 | 44 | Rz25 | 38.132RZ | TURNING CUTTING PARAMETER NOT OK (RPM- 1800, FEED-0.12) |  | CUTTING PARAMETER CHANGE TO 2500 RPM & 0.08 FEED RATE. & SURFACE ACHIEVED BELOW Rz6.0 | PROGRAM TO BE FINALISE & CONTROLLED. | MAHESH | 15.02.19 | COMPLETED

## M4
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR M4 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/ Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | M4 | METHOD | T0/PP0 | FORGING | LUG RADIUS OBSERVED NG |  | C 0.8 ~ 1.5 | 1.726 ~ 2.209 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED | SOMANATH | 10.02.19 | COMPLETED
2 | M4 | TOOL | T0/PP0 | TURNING-2 | IDENTIFICATION GROOVE NOT POSSIBLE WITH WNMG INSERT TOOL |  | DEPTH 0.1~0.3, WIDTH 2~2.5 | FORM NOT OK | EXISTING TOOL TOUCH TO OD WHLIE GROOV MAKING. |  | ETQNL SPECIAL TOOL & TNMG 0.8 IS ARRANGED FOR TRIAL. | ETQNL SPECIAL TOOL & TNMG 0.8 TOOL ADD IN TOOL LIST/PROCESS SHEET. | MAHESH RAO, PRAMOD | 10.01.19 | COMPLETED
3 | M4 | TOOL | T0/PP0 | HOBBING | DEBURRING BURR OBSERVED ON PART |  | BURR FREE PART | BURR | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | BWL- PE |  | UNDER PROGRESS.
4 | M4 | JIG / FIXTURE | T0/PP0 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.05 | 0.03~0.06 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
5 | M4 | METHOD | PP1 | TURNING-2 | DENT OBSERVED ON PART FACE |  | APPEARANCE | VISUAL NG | AIR BLOW NOT DONE BEFORE PART LOADING. | ロケーターエアーブローなし | EVERY PART AIR CLEANING DONE ON STOPPER | AUTOMATION TO BE PROVE OUT & ENSURE AIR BLOW ON, BEFORE LOADING. | MANOHAR/ MAHESH | 20.04.19
6 | M4 | METHOD | PP1 | SHAVING | SHAVING SPAN VARIATION OBSERVED | 5 | SPAN 15.760 - 0.03 / -0.06 | . -0.016 MAX / -0.068 MIN | HOBBING PCD RUNOUT IMPACT | ホブの管理ができていない。 | PART ARE SEGEGATED WITH HOBBING PCD 0.02 MM FOR SPAN MAINTAIN | 1) OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | BWL- PE | 25.03.19 | UNDER PROGRESS.
7 | M4 | TOOL | PP1 | SHAVING | SHAVING PROFILE TC OBSERVED NG |  | LEAD & PROFILE NG (FF-20 FQ-17) | FF 24 FQ 19 | CUTTER RESHARPENING NOT OK | カッター再研が悪い、ひずみ検証ができていない。 | CUTTER RESHAREPING DONE & CUTTING PARAMETERS ARE CHANGED | CUTTER RESHARPENING PROGRAM TO FREEZE AS PER DISTORTION STUDY & CONTROL THE PROGRAM. | HARISH | 10.01.19 | COMPLETED
8 | M4 | METHOD | PP1 | HOBBING&SHAVING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD- 46.510 ~ 46.540 SPAN - (15.690) | 46.552 15.682 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 25.03.19 | UNDER PROGRESS.
9 | M4 | INSPECTION | PP0 | LAYOUT | Apperarence | 76 | Apperarence | Deburring cutter mark | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | BWL- PE | 25.03.19 | UNDER PROGRESS.

## M5
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GEAR M5 | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | M5 | METHOD | T0/PP0 | FORGING | DIE LIFE IS LESS, KIDNEY RADIUS UNDER SIZE OBSERVED |  | 2±0.5 | 1.067 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.04.19
2 | M5 | TOOL | T0/PP0 | TURNING-2 | IDENTIFICATION NOT POSSIBLE WITH WNMG INSERT TOOL |  |  |  | EXISTING TOOL TOUCH TO OD WHLIE GROOV MAKING. |  | ETQNL SPECIAL TOOL & TNMG 0.8 IS ARRANGED FOR TRIAL. | DNMG TOOL ADD IN TOOL LIST/PROCESS SHEET. | MAHESH RAO, PRAMOD | 10.01.19 | COMPLETED
3 | M5 | METHOD | T0/PP0 | TURNING-2 FORGING | PART FACE UNCLEAR |  | APPEARANCE | VISUAL NG | FORGING DESIGN NOT OK |  | FORGING STOCK TO BE MODIFIED | FORGING & TURNING PROCESS SHEET NEED TO UPDATE. | SOMANATH | 20.01.19 | COMPLETED
4 | M5 | METHOD | T0/PP0 | SHAVING | GEAR PCD RUNOUT NOT OK (0.060 AGAINST 0.025) | PROCESS SHEET SPEC | 0.025 | 0.06 | HOBBING PCD RUNOUT IMPACT | ホブの管理ができていない。 | PART ARE SEGEGATED WITH HOBBING PCD 0.02 MM FOR SPAN MAINTAIN | 1) OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | NARENDRA SURESH | 20.04.19 10.04.19
5 | M5 | JIG / FIXTURE | T0/PP0 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) | PROCESS SHEET SPEC | 0.035 | 0.03~0.055 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
6 | M5 | METHOD | T0/PP0 | HONNING | BORE DIA IS UNCLEAR |  | APPEARANCE | VISUAL NG | BORE DIAMETER DISTORTION UNEVEN (TAPERED) |  | TURNING BORE DIAMETER REDUCED FOR MORE HONING STOCK. | 1) BORE DIAMETER DISTORTION STUDY TO BE RE-CHECK & REVISE THE TURNING BORE DIAMETER SPEC. 2) TURNING 1&2 PROCESS INTERCHANGE & EVALUATE THE DISTORTION PATTERN & DECIDE THE PROCESS. | CFT | 25.04.19 29.03.19 | UNDER PROGRESS
7 | M5 | FORGING | PP1 | FORGING | KIDNEY RADIUS FOUND NG | 79 | KIDNEY SIDE FORGING RADIUS 0.8 / 1.5 | 2.2 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.02.19 | COMPLETED
8 | M5 | METHOD | PP1 | TURNING-1 | BURR OBSERVED ON KIDNEY TURNED WALLS AND CHAMFER. |  | APPEARANCE | VISUAL NG | ROUGH TO FINISH STOCK NOT BALANCED. | 仕上げ取り代はいくつ？確認してください。 | REWORK DONE TO REMOVE BURR. | ROUGH TO FINISH STOCK BALANCE & TRIAL TO BE DONE FOR BURR ELIMINATION, & PROGRAM TO BE FREEZE. | MAHESH/MANOHAR/PRAMOD | 06.04.19 | UNDER PROGRESS.
9 | M5 | METHOD | PP1 | HOBBING | DEBURRING BURR OBSERVED ON PART |  | APPEARANCE | VISUAL NG | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | CFT | 02.04.19 | UNDER PROGRESS.
10 | M5 | METHOD | PP1 | SHAVING | SHAVING SPAN VARIATION OBSERVED | 75 | SPAN 21.113 -0.026 / -0.053 | . -0.012 MAX / -0.061 MIN | HOBBING PCD RUNOUT IMPACT | ホブの管理ができていない。 | PART ARE SEGEGATED WITH HOBBING PCD 0.02 MM FOR SPAN MAINTAIN | 1) OBD SPEC CONTROL PARAMETER CHANGE IN COSTOMER DRAWING BY SPEC CHANGE REQUEST. 2) TWO PIECE TO ONE PIECE SHAVING LOCATOR TO BE DESIGN & TRIAL TO BE DONE. | BWL- PE |  | UNDER PROGRESS.
11 | M5 | METHOD | PP1 | HOBBING&SHAVING | SPAN OR OBD CONFIRMATION | PROCESS SHEET SPEC | OBD - 51.620 ~ 51.650 SPAN - (21.06) | 51.656 21.052 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE |  | UNDER PROGRESS.
12 | M5 | INSPECTION | PP0 | LAYOUT | R2±0.5 | 14 | R2±0.5 | 0.19~0.3 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.04.19
13 | M5 | INSPECTION | PP0 | LAYOUT | Span21.133-0.026/-0.053 | 75 | Span21.133-0.026/-0.053 | -0.35/-0.62 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE |  | UNDER PROGRESS.
CUSTOMER REQUIREMENT IS ALL TEETH GRAPH (4 TEETH GRAPH CAN BE MAKE IT OK)+J4:K4 FF- 13.1 (OK) FQ- 27.8 (NG)

## RSD
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | RSD | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | RSD | METHOD | T0/PP0 | FORGING | LUG PROFILE IS DAMAGED (STEP) |  | APPEARANCE | VISUAL NG | TRIMMING DIE IS MODIFIED |  | TRIMMING DIE DRAWING IS UPDATED | TRIMMING DIE DRAWING CONTROL COPY ISSUE TO CONCERN. | SOMANATH | 26.03.19 | COMPLETED
2 | RSD | METHOD | T0/PP0 | OUTSOURCE TURNING | TURNING OD NG |  | 25.5-0.3 | 25.56 | OUTSOURCE DRAWING SPEC NOT OK |  | OUT SOURCE DRAWING UPDATED AS PER FINAL REQUIREMENT | UPDATED OUT SOURCE DRAWING CONTROL COPY ISSUED TO CONCERN SECTIONS. | ASHOK | 20.01.19 | COMPLETED
3 | RSD | SOZAI | PP1 | TURNING | RATCHET CHAMFER FOUND NG |  | C1+0.2 | 0.81 | FORGING CONSTRAINT | 外注守れないのか？ | CHAMFER OK PART SEGGRIGATED | SPEC TO BE REVISED AS PER FORGING SHAPE THROUGH SPEC CHANGE REQUEST FROM HMSI | BWL- PE |  | UNDER PROGRESS.

## PKS
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | PKS | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | PKS | JIG / FIXTURE | T0/PP0 | TURNING-1 | JAWS RADIUS TOUCH TO STOPPER, SO MOUNTING NOT POSSIBLE |  | STRAIGHT FORM | RADIUS FORM | SUPPLIER/MAP DRAWING NOT MATCH WITH ACTUAL PART. |  | JAWS REWORKED FROM RADIUS TO STRAIGHT IN TOOL ROOM | JAWS DESIGN REVISE FOR STRAIGHT FACE INSTEAD OF RADIUS. | MAHESH P, SHIVA | 05.01.19 | COMPLETED
2 | PKS | TOOL | T0/PP0 | TURNING-1 | ROUGH BORING IS NOT POSSIBLE TO PROCESS |  |  |  | EXISTING TOOL COMMON CONSIDERED. |  | A12M STFCR TOOL IS USED INSTEAD OF S12M STFCER | A12M STFCR TOOL ADD IN TOOL LIST & PROCESS SHEET. | MAHESH & PRAMOD | 25.03.19 | UNDER PROGRESS
3 | PKS | TOOL | T0/PP0 | TURNING-2 | IDENTIFICATION NOT POSSIBLE WITH STFCL INSERT TOOL |  | DEPTH 0.1~0.3, WIDTH 2~2.5 | FORM NOT OK | EXISTING TOOL COMMON CONSIDERED. |  | STFCR TOOL CHANGED FROM STFCL TOOL HOLDER | STFCR TOOL HOLDER ADD IN TOOL LIST & PROCESS SHEET. | MAHESH & PRAMOD | 25.03.19 | UNDER PROGRESS
4 | PKS | JIG / FIXTURE | T0/PP0 | HOBBING | PART FACE BURR OBSERVERD ON ROOT |  | APPEARANCE | VISUAL NG | BOTTOM FIXTURE OUTER DIAMETER HIGHER SIDE DESIGNED (0.5 MM GAP AGAINST 1.0 MM) |  | BASE LOCATOR DIAMETER REWORKED IN TOOL ROOM | BASE LOCATOR DRAWING TO BE REVISED UNDERSIZE BY 0.5MM TO 1.0MM | AMBIKA | 15.12.18 | COMPLETED
5 | PKS | JIG / FIXTURE | T0/PP0 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.035 | 0.03~0.055 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
6 | PKS | METHOD | T0/PP0 | TURNING-2 | RATCHET ID & OD TURNING BURR FOLD |  | APPEARANCE | VISUAL NG | RACHET TURNING DIRECTION SAME WITH EXISTING(KTE). |  | RACHET TURNING TOOL DIRECTION CHANGED.(TOOL HOLDER CHANGED) | REVISED TOOL HOLDER (ADJNR 20X20) ADD IN TOOL LIST & PROCESS SHEET. | MAHESH & PRAMOD | 25.03.19 | UNDER PROGRESS
7 | PKS | METHOD | T0/PP0 | FORGING | RATCHET TOP FACE WIDTH FOUND NG |  | 1±0.1 | 1.15 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.02.19 | COMPLETED
8 | PKS | METHOD | PP1 | HOBBING | SPAN OR OBD CONFIRMATION |  | OBD-43.890~43.920 SPAN - (13.090) | 43.882 13.091 | HOBBING PCD RUNOUT IMPACT | スパンとOBDの関係性はあっていたのか？ | PARTS MADE CONSIDERING OBD, KEEPING SPAN AS REFRENCE | OBD OR SPAN WHICH IS TO BE MAINTAINED TO BE CONFIRMED BY CUSTOMER AGAINST RAISED HINANIYO SHEET | BWL- PE | 25.03.19 | UNDER PROGRESS.
9 | PKS | INSPECTION | PP1 | LAYOUT | CHAMFER C 0.2 ~0.3 (OPP TO RATCHET SIDE) |  | C 0.2 ~ 0.3 | 0.32 ~0.29 | FORGING CONSTRAINT | 外注守れないのか？ | CHAMFER OK PART SEGGRIGATED | SPEC TO BE REVISED AS PER FORGING SHAPE THROUGH SPEC CHANGE REQUEST FROM HMSI | BWL- PE | 25.03.19 | UNDER PROGRESS.
10 | PKS | INSPECTION | PP1 | LAYOUT | RADIUS 0.3±0.5 NG | 45 | RADIUS 0.3±0.5 | 0.96 | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.02.19 | COMPLETED
11 | PKS | INSPECTION | PP1 | LAYOUT | RATCHET ANGLE 58°±1°30' | 41 | 58°±1°30' | 53°44' | DIE DESIGN NG |  | DIE MODIFICATION TO REDUCE LOAD ON LUG INSIDE AREA | DIE DRAWING TO BE MODIFIED & TRIAL TO BE DONE FOR LIFE IMPROVEMENT. | SOMANATH | 10.02.19 | COMPLETED

## SC
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | SHAFT COUNTER | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | SHAFT COUNTER | METHOD | PP0 | FORGING HEAT TREATMENT | SPLINE DIMENSION OVER BALL IS NG | 4B | OBD 22.112 (-0.03/-0.067) | . -0.065/-0.074 | IN COLD FORGING, SPLINE OBD DISTORTION NOT CONSIDERED. |  | PART SEGGRIGATE & USED FOR EVENTS. | AS PER HT DISTORTION EVALUATION SPLINE OBD CORRECT IN COLD FORGING | PANKAJ DHIMAN | 20.04.19 | UNDER PROGRESS
2 | SHAFT COUNTER | METHOD | PP0 | OIL HOLE DRILLING | OIL HOLE ANGLE NG | 23 | Angle120°±1°30̕ | 112°42´/114°15´ | COMMON CHAMFER TOOL USED (114º) | 形状測定機にて中心を拾っているか？ | 120° CHAMFER TOOL USED. | 1) 120º CHAMFER TO BE ARRANGE & UPDATE IN TOOL & PROCESS SHEET 2) CHAMFER COMMON SPEC REQUEST TO HMSI THROUGH SPEC CHANGE REQUEST. | HARISH / PRAVEEN | 25.03.19 15.04.19 | UNDER PROGRESS
3 | SHAFT COUNTER | METHOD | PP0 | OIL HOLE DRILLING | 1) OIL HOLE CHAMFER DIA NG BY 0.01 mm 2) DIMENSION 13 [+0.1] NG |  |  |  | PART NOT BUTTING PROPERLY | 形状測定機にて中心を拾っているか？ | PART RESTING VBLOCK CLEANED EVERY TIME BEFORE LOADING THE PARTS | AUTOMATION TO BE PROVE OUT & ENSURE AIR BLOW ON, BEFORE LOADING. | PRAVEEN | 20.04.19 | UNDER PROGRESS
4 | SHAFT COUNTER | INSPECTION | PP0 | LAYOUT | CIRCUMFERENCIAL POSITION OF OIL HOLES ARE OPTIONAL. BUT OIL HOLE SHOULD BE BORED AT TEETH CENTER | 102 | TEETH CENTER | SHIFT FROM TEETH CENTER | PART ORIENTATION LOCATOR SETTING NOT OK & IN SETUP APPROVAL TEETH CENTER NOT CONFIRMED DUE TO CHECK POINT NOT AVAILABLE. |  | PART SEGGRIGATE & HANDOVER FOR EVENT. | PART TEETH ORIENTATION LOCATOR SETTING TO BE VERIFIED & TEETH CENTER CHECK POINT TO BE ADD IN PROCESS SHEET & SAME ENSURE IN SETTING APPROVAL. | ASHOK | 28.03.19 | UNDER PROGRESS
5 | SHAFT COUNTER | INSPECTION | PP1 | LAYOUT | APPEARANCE |  | APPEARANCE | SPLINE BURR | ROUGH TO FINISH STOCK NOT BALANCED. | 仕上げ取り代はいくつ？確認してください。 | REWORK DONE TO REMOVE BURR. | ROUGH TO FINISH STOCK BALANCE & TRIAL TO BE DONE FOR BURR ELIMINATION, & PROGRAM TO BE FREEZE. | MAHESH/MANOHAR/PRAMOD | 06.04.19 | UNDER PROGRESS
6 | SHAFT COUNTER | INSPECTION | PP0 | LAYOUT | OBD 22.112 (-0.03/-0.067) | 4B | OBD 22.112 (-0.03/-0.067) | . -0.065/-0.074 | IN COLD FORGING, SPLINE OBD DISTORTION NOT CONSIDERED. |  | PART SEGGRIGATE & USED FOR EVENTS. | AS PER HT DISTORTION EVALUATION SPLINE OBD CORRECT IN COLD FORGING | PANKAJ DHIMAN | 20.04.19 | UNDER PROGRESS
7 | SHAFT COUNTER | INSPECTION | PP0 | LAYOUT | Angle120°±1°30̕ | 23 | Angle120°±1°30̕ | 112°42´/114°15´ | COMMON CHAMFER TOOL USED (114º) | 形状測定機にて中心を拾っているか？ | 120° CHAMFER TOOL USED. | 1) 120º CHAMFER TO BE ARRANGE & UPDATE IN TOOL & PROCESS SHEET 2) CHAMFER COMMON SPEC REQUEST TO HMSI THROUGH SPEC CHANGE REQUEST. | HARISH / PRAVEEN | 25.03.19 15.04.19 | UNDER PROGRESS
8 | SHAFT COUNTER | INSPECTION | PP0 | LAYOUT | Chamfer Ø3±0.2 | 25 | Chamfer Ø3±0.2 | 2.89/3.21 | PART MIS LOCATED IN FIX. DUE TO LOOSE CHIPS ACCUMULATION. |  | PART SEGGRIGATE & HANDOVER FOR EVENT. | 1) 100% MANUALY AIR CLEANING BEFORE PART LOADING IN FIXTURE. 2) AIR / COOLANT CLEANING FEASIBILITY TO BE CHECK & IMPLEMENT. | PRAVEEN & MAINT | 18.04.19 | UNDER PROGRESS

## SM
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | SHAFT MAIN | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | SHAFT MAIN | METHOD | PP0 | TURNING | GROOVE DISTANCE NG 61.3 [-0.1] | 37 | 61.3-0.1 | 59.82 ~ 59.92 | INSPECTION ERROR, WRONG REFERENCE FACE INSPECTION. | ？ | GROOVE DISTANCE INSPECTED AS PER PROCESS SHEET, AWEARNESS TRAINING GIVEN TO ENGG. | DIMENSION MAINTAIN AS PER PROCESS SHEET. | PRAVEEN SHIVANAND | 20.01.19 | COMPLETED
2 | SHAFT MAIN | METHOD | PP0 | OIL HOLE DRILLING | OIL HOLE ANGLE NG 120° | 74 | 120° ± 1°30' | 114°50´ | COMMON CHAMFER TOOL USED (114º) | 形状測定機にて中心を拾っているか？ | 120° CHAMFER TOOL USED. | 1) 120º CHAMFER TO BE ARRANGE & UPDATE IN TOOL & PROCESS SHEET 2) CHAMFER COMMON SPEC REQUEST TO HMSI THROUGH SPEC CHANGE REQUEST. | HARISH / PRAVEEN | 25.03.19 15.04.19 | UNDER PROGRESS
2 | SHAFT MAIN | METHOD | PP0 | OIL HOLE DRILLING | OIL HOLE CHAMFER DIA NG NEAR THREAD PORTION | 76 | 3±0.2 | Sline teeth damaged while drilling | COMMON CHAMFER TOOL USED (Ø5.0) | 形状測定機にて中心を拾っているか？ | CHAMFER TOOL DIAMETER REDUCED BY 1.0MM. | CHAMFER TOOL DRAWING CHANGE FOR DIAMETER FROM Ø5.0 TO Ø4.0 & ARRANGE. TOOL LIST & PROCESS SHEET UPDATE FOR THE Ø4.0 TOOL | HARISH / PRAVEEN | 30.03.19 | UNDER PROGRESS
3 | SHAFT MAIN | METHOD | PP0 | OIL HOLE DRILLING | OIL HOLE POSITION 16.5 NG | 28 | 16.5±0.2 | 17.354 | INSPECTION ERROR (CMM MACHINE) | 検査ミス（詳細確認要） | INSPECTION METHOD CORRECTED. | INSPECTION TRAINING TO CMM OPERATOR & UPDATE SKILL MATRIX. | SHIVANAND | 12.1.19 | COMPLETED
3 | SHAFT MAIN | METHOD | PP0 | TURNING | GEAR FACE ROUGHNESS NG | 53 | Rz 25 |  | CUTTING FEED MORE | 刃具寿命と、規格は？ | CUTTING FEED DECREASE FROM 0.2 TO 0.1MM/REV | TURNING PROGRAM TO BE FREEZED & CONTROL COPY RECORD. | PRAVEEN | 20.02.19 | COMPLETED
4 | SHAFT MAIN | METHOD | PP0 | STARGHITENING AFTER HT | RADIAL RUNOUT OF TEETH & SPLINE WAS NG | 98 | 0.056 | 0.1 | STRAIGHTNING OPERATION MISSING | 熱処理前（0.07ミリ）で管理してどうか？今は？ | NEW LOT PROCESSED STRAIGHTNING BERFORE GRINDING | ENSURE PART PROCESS AS PER PSM & STRICTLY FOLLOW LOT TAG. | GANESH & SUNDAR | 22.01.19 | COMPLETED
4 | SHAFT MAIN | METHOD | PP0 / PP1 | DEBURRING | SPLINE DEBURRING TOOL NOT AVAILABLE |  | APPEARANCE (TOOL NOT AVAILABLE) | VISUAL NG | DEBURRING TOOL COMMON CONSIDERED & DESIGN NOT VERIFIED. | デバリングツールなぜないのか？ | INDIVIDUAL SPLINE DEBURRING DONE. | NEW DEBURRING TOOL HOLDER TO BE DESIGNE, ARRANGE & PROVEOUT. | SOMANATH | 10.04.19 | UNDER PROGRESS.
5 | SHAFT MAIN | JIG / FIXTURE | PP0 | OIL HOLE DRILLING | REST PAD FOULING WHILE CLAMPING |  | PART CLAMP BY REST PAD | REST PAD FAULING | OIL HOLE DRILLING FIXTURE COMMON CONSIDERED & DESIGN NOT VERIFIED. | 図面間違い？図面確認 | REST PAD MODIFIED AS PER REQUIRED LENGTH | NEW REST PAD TO BE DESIGN. ARRANGE & PROVEOUT. | SOMANATH | 10.04.19 | UNDER PROGRESS.
5 | SHAFT MAIN | METHOD | PP0 | GRINDING | JOB DRIVER NOT OK |  | PART PROPERLY HOLD | DRIVER LENGTH & DIAMETER NOT OK. | COMMON JOB DRIVER CONSEDERED & DESIGN NOT VERIFIED. | 何が問題？ | EXISTING JOB DRIVER REWORKED. | NEW JOB DRIVER DESIGNED, ARRANGE & PROVEOUT. | SOMANATH | 20.02.19 | COMPLETED
6 | SHAFT MAIN | METHOD | PP0 | FACING CENTERING | CENTER DRILL OPENING DIA. MINIMUM SIDE CENTER HOLE CHAMFER 5 +0.2 Actual 4.94 |  | 5 +0.2 | 4.94 | STANDERD CENTER DRILL USED FOR FACING CENTERING. | 何が問題？ | OPENING DIAMETER TOLERANCE CONSIDERED AS ±0.1 (CENTER DRILL ONLY FOR MACHINING REF.) | CENTER DRILL OPENING DIAMETER TOLERANCE TO BE REVISED FROM CUSTOMER AS PER STANDARD DRILL (i.e. ±0.2) THROUGH SPEC CHANGE REQUEST. | SURESH | 20.04.19 | UNDER PROGRESS.
6 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | (Lead &Profile)Gear profile | 3 | (Lead &Profile)Gear profile | NG
7 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | Oil hole position 16.5±0.2 | 28 | Oil hole position 16.5±0.2 | 17.354
7 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | Hight 61.3-0.1 | 37 | Hight 61.3-0.1 | 59.82/59.92
8 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | 155.3±0.25 | 41 | 155.3±0.25 | 156.45/156.55
8 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | 24.9-0.2 | 55 | 24.9-0.2 | 24.519/24.538
9 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | Chamfer 0.5+0.2 | 57 | Chamfer 0.5+0.2 | Thread rolling done
9 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | R0.5-0.2 | 59 | R0.5-0.2 | 0.55
10 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | 120°±1°30´ | 74 | 120°±1°30´ | 114°50´
10 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | ø3±0.2 | 76 | ø3±0.2 | Gear teeth damaged while drilling
11 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | PCD-0.056 | 98 | PCD-0.056 | 0.05/0.1
11 | SHAFT MAIN | INSPECTION | PP0 | LAYOUT | HEIGHT 100.8±0.25 NG |  | HEIGHT 100.8±0.25 | 101.41 | SAID DIMENSION WAS NOT CONSIDERED IN SOFT PROCESS |  | LOT REJECTED & NEW LOT | PROCESS SHEET UPDATED WITH THE TOLERANCE FOR THE LENGTH CONTROL. | SURESH | 20.12.18 | COMPLETED
12 | SHAFT MAIN | INSPECTION | PP1 | LAYOUT | GEAR TEETH END BURR |  | APPEARANCE | VISUAL NG | ROUGH TO FINISH STOCK NOT BALANCED. | 仕上げ取り代はいくつ？確認してください。 | REWORK DONE TO REMOVE BURR. | ROUGH TO FINISH STOCK BALANCE & TRIAL TO BE DONE FOR BURR ELIMINATION, & PROGRAM TO BE FREEZE. | PRAVEEN | 06.04.19 | UNDER PROGRESS.
12 | SHAFT MAIN | INSPECTION | PP1 | LAYOUT | PCD MORE | 98 | PCD 0.056 | 0.062 | STRAIGHTNING OPERATION NOT VALIDATE |  | PART SEGGRGATE & HANDOVER FOR EVENT. | STRAIGHTNING PROCESS TO BE VALIDATE. | ASHOK | 10.04.19 | UNDER PROGRESS.

## SKS
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | SKS | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | SKS | METHOD | PP0 | TURNING | Jaw clamp mark on part od |  | APPEARANCE | VISUAL NG | JAWS WIDTH WAS NOT OK (COMMON JAWS SIMULATION NOT DONE) |  | JAWS WIDTH MODIFIED (12 MM TO 6.0 MM) | JAWS DESIGN TO BE MODIFIED & ARRANGE. | SOMANATH | 05.04.19 | under process
2 | SKS | METHOD | PP0 | DEBURRING | deburring mark on part od as ommit teeth is present |  | APPEARANCE | VISUAL NG | DEBURRING PROCESS CONSTRAINT. |  | MANUAL DEBURRING BY MATING PART PASSING. | SPEC CHNGE REQUEST TO BE INITIATED FOR DEBURRING MARK ALLOWED | Narendra | NEW LOT | Under process
3 | SKS | TOOL | PP0 | DEBURRING | Tool holder and deburring Cutter to be order |  | APPEARANCE | Burr issue Fitment NG | Existing cannot be used as the spline details are different |  | MANUAL DEBURRING BY MATING PART PASSING. | SPEC CHNGE REQUEST TO BE INITIATED FOR DEBURRING MARK ALLOWED Other feasibilities to be checked for deburring tool develoment | SHIVANAND | NEW LOT | Under process
4 | SKS | MACHINE | PP0 | clip hole drilling | clip hole automation setup to be devlop by supplier. |  |  |  | DESIGN FEASIBILITY & SIMULATION NOT CHECKED |  | Run in Manual setup | Machine modification to be done with the help of Maker to suite K0NA model | Somnath | 12.1.19 | Completed

## GPD
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GPD | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | GPD | METHOD | T0/PP0 | GRT | CENTER DISTANCE IS UNDER SIZE |  | 80.003±0.029 |  | IN DISTORTION STUDY CD PARAMETER NOT CHECKED. |  | AS PER DISTORTION STUDY SPAN REVISED&NEW LOT MADE | AS PER DISTORTION STUDY SPAN SPEC UPDATED IN PROCESS SHEET | PRASHANTH & NARENDRA | 20.01.19 | COMPLETED
2 | GPD | JIG / FIXTURE | T0/PP0 | HONING | PART FACE RUNOUT VARIATION (OUT OF SPEC) |  | 0.035 | 0.03~0.055 | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED
3 | GPD | METHOD | PP1 | HOBBING | DEBURRING BURR OBSERVED ON PART |  | APPEARANCE (NO BURR) | VISUAL NG | DEBURRING TOOL SETTING NG. | デバ高さ設定、規格の標準なし | DEBURRING TOOL RESHARPENING DONE & SETUP CORRECTED. | DEBURRING TOOL FEED MARK ACCEPTANCE & BURR HEIGHT ACCEPTANCE STANDARD CHANGE POINT RAISE & APPROVAL FROM HMSI. | CFT | 02.04.19 | UNDER PROGRESS.
4 | GPD | INSPECTION | PP0 | LAYOUT | Face runout 0.03 | 10 | Face runout 0.03 | 0.04 (1/ 5 parts) | FIXTURE DESIGN & MANUFACTURING NOT OK, (PART LOCATING PIN POSITION NOT OK, GUIDE BUSH HEIGHT NOT OK). | 図面未確認 | HONING FIXTURE PIN LOCATION REPAIR & GUIDE BUSH HEIGHT REPAIRED. | FIXTURE RETURN TO SUPPLIER & MODIFY & PROVEOUT. | MAKER / NARENDRA | 20.02.19 | COMPLETED

## GPDN
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | GPDN | [9 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | GPDN | JIG / FIXTURE | T0/PP0 | HOBBING | PART FACE BURR OBSERVERD ON ROOT |  | NO BURR | ROOT AREA BURR | BOTTOM FIXTURE OUTER DIAMETER HIGHER SIDE DESIGNED (0.5 MM GAP AGAINST 1.0 MM) |  | BASE LOCATOR DIAMETER REWORKED IN TOOL ROOM | BASE LOCATOR DRAWING TO BE REVISED UNDERSIZE BY 0.5MM TO 1.0MM | AMBIKA | 15.12.18 | COMPLETED
2 | GPDN | JIG / FIXTURE | T0/PP0 | HARD TURNING | PART STOPPER NOT ABLE TO ASSEMBLE |  | STEP REQUIRED | STEP NOT AVAILABLE | SUPPLIER DESIGN NOT UPDATED. |  | STOPPER REWORKED AS PER EXISTING LOCATOR. | INFORM TO MAKER FOR REVISE THE STOPPER DRAWING & ARRANGE NEW STOPPER. | MAKER / NARENDRA | 20.12.18 | COMPLETED
3 | GPDN | METHOD | T0/PP0 | GRT | CENTER DISTANCE IS UNDER SIZE |  | 120.07±0.034 | 120.07~120.022 | AFTER INDUCTION HARDENING / HARD TURNING SPAN & OBD CONFIRMED AS PER FINAL DRAWING, CD NOT CONFIRMED. |  | CD GAUGE SETTING & PART CONFIRMED. | CD CHECK POINT TO BE ADD IN INDUCTION/HARD TURNING PROCESS SHEET. | CFT | 22.03.19 | COMPLETED
3 | GPDN | METHOD | PP1 | HARD TURNING | PCD RUNOUT NG |  | 0.04 | 0.015 ~0.045 | SETTING MASTER NOT AVAILABLE | スパンとOBDの関係性はあっていたのか？ | MINIMUM PCD PART MASTER MADE FOR SETTING MASTER. | HSS PART MASTER TO BE ARRANGE. | NARENDRA | 30.04.19 | COMPLETED

## CR
KONA-PROBLEM POINTS&ACTIONS | [5 empty] | CON ROD | [8 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/Standard | Actual | root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | CON ROD | JIG / FIXTURE | PP0 | BIG END SMALL END BORING & CHAMFERING | 1.BIG END OVALITY OBSORVED 0.016, 2.SMALL END HEAVY BURR OBSORVED IN KALYANI SUPPLIER, 3.FIXTURE DESIGN NOT REGID TO CLAMP PROPERLY, 4.SUPPLIERS SAME SET UP CANT ABLE TO RUN DUE TO FORGING 5.VARIATION(WALL THICK NESS COMING) 6.Only Two stations proved and other 2+4 station need to be proved |  |  |  | 1. Fixture Design to be improved to eliminate Ovality Issue 2.Supplier part 3.Fixture Design to be improved 6. Fixtures to be ordered and proved | PARTS PROCESSED & IN FINAL STAGE PARTS MEET THE DRAWING SPECIFICATION. | BURR IN PARTS EVIDENT TO SUPPLIER & COUNTERMEASURE REQUEST FROM SUPPLIER WITH IMPROVED SAMPLES. | 1., Mahesh 2. Pankaj san 6. Suresh San | 20.04.19 | UNDER PROGRESS
2 | CON ROD | JIG / FIXTURE | PP0 | OIL HOLE DRILLING | MACHINE REPEATIBILITY ISSUE,(45°ANGLE,7.5±0.1 MM DISTANCE ) OIL HOLE HOLE OD CHAMFER DRILL STEP MARK OBSORVED(SET UP TIME ALSO TAKING MORE TIME |  |  |  | SPM machine-there is no datum available for different Models | Master Part developed and setting is doing as per the same | Need to discuss with Maker for the feasibility of model change over with minimum time | Suresh san | 10.02.19 | COMPLETED
3 | CON ROD | JIG / FIXTURE | PP0 | BIG END HONING | FACE RUN OUT OBSORVED ON STATION 2,ROUGHNESS 0.8Rz INSPECTION PARAMETERS AS PER STANDARED NOT MAINTAINED WRONG REPORT DUE TO THAT PARTS HAS BE REJECTED, |  |  |  | Roughness Issue: Inspection Standard was not clear Existing Ledges Grade was not Ok for the given roughness Face R/O: Floating is not proper | EXISTING LEDGES USED . | NEW GRADE LEDGES TO BE ARRANGE FOR TRIAL & PROVEOUT THE ROUGHNESS. | Suresh /Gangadhar | 2019-04-18 | UNDER PROGRESS
4 | CON ROD | JIG / FIXTURE | PP0 | SMALL END FINE BORING | 1. Rz 3.2 NOT ACHVED ON EXISTING INSERT, FOR TRIAL KORLOY MAKE (TPMT090204MPCN1500) 2.NC machine is not proved out |  |  |  | FINE BORING INSER GRADE NOT SUITABLE FOR ACHIEVE Rz3.2. | NEW KORLOY MAKE NEW GRADE INSERT TRIAL DONE & ROUGHNESS FOUND OK. | NEW KORLOY MAKE NEW GRADE INSERT (TPMT090204MPCN1500) VALIDATION TO BE DONE & UPDATE IN TOOL LIST & PROCESS SHEET. | Suresh / Gangadhar / Pramod | 2019-04-18 | UNDER PROGRESS
5 | CON ROD | JIG / FIXTURE | PP0 | VISUAL | OIL HOLE DRILLING GO GAUGE PASSING TIME SMALL END ID DAMAGED |  |  |  | INSPECTION ERROR | Awareness given to inspection personnel to take care of any unwanted contact during checking | PLUG GAUGE DESIGN TO BE CHECK & REDUCE THE PLUG /PIN LENGTH , TO AVOID THE UNWANTED CONTACT. | MAHESH | 25.03.19 | UNDER PROGRESS
6 | CON ROD | JIG / FIXTURE | PP0 | BEND & TWIST | Face Dent mark observed after Bend and Twist Inspection during PP0 trial |  |  |  | Used existing fixture for inspection and due to slot width not suiatble for K0NA part during checking mark has generated | - | Fixture slot provided seperately for K0NA/K0LA parts | Suresh san | 25.03.19 | UNDER PROGRESS

## SHAFT CAM
KONA-PROBLEM POINTS&ACTIONS |  |  |  |  | Cam shaft | [10 empty] | 2019-03-01
S.No |  | Area | Event/Trial | Operation | PROBLEM POINT | Dim Ballon No | Spec/ Standard | Actual | Root cause | Root cause | Temperory Action | Permanent Action | Responsibility | Target | STATUS | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
3 | CAM | JIG / FIXTURE | PP0& PP1 | FACING AND CENTERING | GAUGE MASTER READING IS NOT MATCHING WITH ACTAUAL |  |  |  | GAUGE MASTER NG |  | CHECKED WITH MASTER PART | NEW GAUGE MASTER NEED TO BE PROCURED | SURESH SAN | 2019-04-05 | UNDER PROGRESS
4 | CAM | MACHINE | PP0 | TURNING-1 (L5) | X-AXIS REPEATABILITY ISSUE |  |  |  | PLAY OBSERVED IN X-AXIS DUE T TURCITE GOT DAMAGED |  | SAMPLE MADE IN L-2 AND TO BE USED UNTIL THE MACHINE ISSUE GET RESOLVED | NEED TO BE REPAIRED | MALLIKARJUN SAN | 2019-04-05 | UNDER PROGRESS
5 | CAM | MACHINE | PP0 | TURNING-2 | X-AXIS REPEATABILITY ISSUE |  |  |  | PLAY OBSERVED IN X-AXIS DUE T TURCITE GOT DAMAGED |  | SAMPLE MADE IN L-2 AND TO BE USED UNTIL THE MACHINE ISSUE GET RESOLVED | NEED TO BE REPAIRED | MALLIKARJUN SAN | 2019-04-05 | UNDER PROGRESS
6 | CAM | MACHINE | PP0 | TURNING-2 | CT MORE (60") |  |  |  | TWO PASS MADE TO AVOID THE STEP MARK |  | SAMPLE MADE IN L-2 AND TO BE USED UNTIL THE MACHINE ISSUE GET RESOLVED | AXIS PLAY NEED TO BE CORRECTED | MALLIKARJUN SAN | 2019-04-05 | UNDER PROGRESS
10 | CAM | JIG / FIXTURE | PP0&PP1 | KW MILLING | SYMMETRICITY CHECKING GAUGE NOT AVAILABLE | [5 empty] | CHECKED IN STANDARD ROOM | SPEICIAL GAUGE DESIGN TO BE DONE AND TO BE PROCURED | SURESH SAN | 2019-03-30 | UNDER PROGRESS
11 | CAM | JIG /FIXTURE | PP0&PP1 | KEW WAY MILLING (L2) | ONLY ONE FIXTURE PROVED |  |  |  | PART ORIENTATION RESTING PAD NG FROM SUPPLIER |  |  | NEW PART TO BE PROCURED | SURESH SAN | 2019-04-05 | UNDER PROGRESS
13 | CAM | TOOLS | PP0&PP1 | DRILLING, REAMING AND TAPPING | Ø10 REAMER SIZE AT MINIMUM, PLUG GAUGE NOT ENTER |  |  |  | REAMER SIZE WAS MINIMUM |  |  | NEW REAMER ORDERED WITH MEAN SIZE | RATHEESH | 2019-03-19 | UNDER PROGRESS
15 | CAM | MACHINE | PP0&PP1 | CAM MILLING | PROFILE REPORT NG |  |  |  | LIFT DATA PROVIDED BY MAKER WAS NG |  |  | CORRECTED LIFT DATA RECEIVED FROM MAKER AND MACHINING PROGRAM CHANGED ACCORDINGLY | RATHEESH | COMPLETED
16 | CAM | MACHINE | PP0&PP1 | CAM MILLING (L5) | BCD RUN OUT AND PARELLISM MORE (UPTO 0.2) |  |  |  | TAILSTOCK PLAY DUE TO SLIDE TURCITE GOT DAMAGED |  |  | NEED TO CORRECT | MALLIKARJUN SAN | 2019-04-10 | UNDER PROGRESS
19 | CAM | MACHINE | PP0 | AXIS GRINDING | SIZE VARIATION ISSUE |  |  |  | IPG NOT WORKING |  | MACHINE RUNNING WITH OUT IPG | IPG CORRECTED WITH THE HELP OF MAKER (ACCRETECH) | SURESH SAN (MAINT.) | COMPLETED
21 | CAM | MACHINE | PP0&PP1 | CAM GRINDING | DIA GOES UNDER SIZE AFTER MACHINE IDLE |  |  |  | NEED TO ANALYSED |  | OFFFSET CORRECTION UPTO 0.2 AFTER MACHINE IDLE | MACHINE CORRECTION TO BE DONE TO AVOID THE VARIATION ISSUE | SURESH SAN (MAINT.) | 2019-04-10 | UNDER PROGRESS
22 | CAM | JIG/FIXTURE | PP0 | CAM GRINDING | PROFILE FOUND NG |  |  |  | HEAD CENTRE DIA LESS AND REFERENCE KEY FOULING WITH PART |  | REFERNCE KEY MODIFIED TO AVOID FOULING WITH PART | CENTRE AND REFE KEY DRAWING TO BE MODIFIED AND TO BE ORDERED | SURESH SAN | 2019-04-10 | UNDER PROGRESS
24 | CAM | MACHINE | PP0&PP1 | DRILLING, REAMING AND MILLING | REAMING ROUGHNESS NG CT MORE-124 SEC |  |  |  | UNDER ANALYSIS |  | RUN WITH VERY LESS FEED TO ACHIEVE THE ROUGHNESS (F30) | NEED TO ESTABLISH | RATHEESH/SANDEEP | 2019-04-10 | UNDER PROGRESS
25 | CAM | MACHINE | PP0&PP1 | DRILLING, REAMING & MILLING | PROFILE BULGE ISSUE AFTER DRILLING AND REAMING |  |  |  | DEFORMATION AFTER DRILLING |  |  | NEED TO CONDUCT DIFFERENT DRILL TRIAL TO AVOID THE BULGE ISSUE | RATHEESH | 2019-04-10 | UNDER PROGRESS
26 | CAM | MACHINE | PP0&PP1 | DRILLING, REAMING & MILLING | Ø4 SIZE VARIATION TOOL LIFE NOT ESTABLISHED |  |  |  | UNDER ANALYSIS |  |  | DRILL AND REAMER TRIALS TO BE DONE TO ESTABLISH THE PROCESS INDUCTION HARDENING VALIDATION TO BE DONE | SANDEEP/GANESH SAN | 2019-04-10 | UNDER PROGRESS
27 | CAM | JIG/FIXTURE | PP0&PP1 | DRILLING, REAMING & MILLING | FIXTURE PROVE OUT DONE FOR ONLY 1 FIXTURE |  |  |  | ONLY 2SETS FIXTURES ARE AVAILABLE, ANOTHER 2 SETS FIXTURES NEED TO BE ORDERED |  |  | ALL FOUR FIXTURES TO BE PROVED | PRAVEEN | 2019-04-10 | UNDER PROGRESS
28 | CAM | MACHINE | PP0&PP1 | BUFFING | MACHINE DISPLAY NOT WORKING |  |  |  | HMI MALFUNCTION |  | SWITCHED ON MACHINE THRU PLC | HMI REPLACEMENT | SURESH SAN (MAINT.) | COMPLETED
29 | CAM | MACHINE | PP0&PP1 | LAPPING | PART DROPPAGE ISSUE |  |  |  | WORK REST DESIGN NOT OK |  |  | WORK REST DESIGN TO BE MODIFIED TO AVOID PART FALLING ISSUE | SURESH SAN | 2019-04-10 | UNDER PROGRESS

## MTP WEGO WITH DEV RAMPUP (hidden)
MASTER TIMING PLAN |  |  |  |  | Confirmation required on completion | ◎ | [49 empty] | 03 | 2017-11-27 |  |  | Preponement of mp from Mar-17 to Feb-17 | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | Cross Functional Team
[5 empty] | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [11 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [54 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE | [5 empty] | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[6 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[6 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [86 empty] | HT | Ganesh san
[6 empty] | WEGO |  | 2017-12-01 W1: T-0; 2018-02-01 W1: T1; 2018-02-01 W3: PL1; 2018-02-01 W4: MP; 2018-03-01 W2: T1; 2018-04-01 W1: PL1; 2018-04-01 W3: MP
[90 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-02-01 W1: 100; 2018-02-01 W3: 300; 2018-02-01 W4: 200; 2018-03-01 W1: 200; 2018-03-01 W2: 200; 2018-03-01 W3: 200; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 400; 2018-04-01 W4: 600; 2018-05-01 W1: 800; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[7 empty] | ACTUAL | 2017-12-01 W3: 5
[5 empty] | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-03-01 W2: 100; 2018-04-01 W3: 200; 2018-04-01 W4: 400; 2018-05-01 W1: 600; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[7 empty] | ACTUAL | 2017-12-01 W3: 5
[5 empty] | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
[5 empty] | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Drawing Release from ME BLR to QA, Prod & Pur BLR | ME-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1; 2018-01-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3; 2018-01-01 W1
[5 empty] | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2; 2018-02-01 W1; 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2
[5 empty] | Sample Making | ME-BLR | PLAN | 2018-01-01 W2: WITH AUTOMATION TRIAL
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-12-01 W1
| New mechanism / New structure | Specifications/drawings |  |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[7 empty] | ACTUAL | 2017-03-16 W4: PO DONE
[5 empty] | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5; 2017-10-16 W4 to 2017-11-01 W5
[5 empty] | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
[5 empty] | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2018-02-01 W1: set up; 2018-02-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
[5 empty] | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
[5 empty] | A'Class tool design (broach,hob shaving) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W3
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design ( honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design (Frazing cutter ) | PE-BWL | PLAN | 2018-04-01 W1: GROTOMAT m/c to be used for MP till frzaing cutters will come.
ACTUAL | bar: 2017-07-16 W3 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
[5 empty] | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4
|  | Jigs |  |  | HT jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-01-01 W4
|  | 3a. Guages |  |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4
|  | 4.Logistics |  |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
ACTUAL | bar: 2017-08-16 W4 to 2017-10-16 W2; 2017-10-16 W4; 2017-12-01 W2 to 2017-12-01 W3
|  | 5.Documentations |  |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
[5 empty] | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W4
[5 empty] | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
[5 empty] | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-12-01 W1 to 2017-12-01 W3
[5 empty] | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | 6.Operator training |  |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | Progress of the P-FMEA |  |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W4
|  | Process design review |  |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W4
| Capacity | Production capacity |  |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
| Quality | Quality concept |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
|  | Issues with changing point |  |  |  | QA-BLR | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | Quality managemant plan |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3; 2018-05-01 W5
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1
[5 empty] | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
|  | 2.Prevention |  |  | ①Design verification | NA | PLAN
ACTUAL
[5 empty] | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W5
[5 empty] | ③QA machine / Pokayoke verification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W4
[5 empty] | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 3.Evaluation of product |  |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
[5 empty] | ②Process capability study | Production,QA | PLAN
ACTUAL
[5 empty] | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W2 to 2018-02-01 W3
ACTUAL
|  | 4.Process verification |  |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 5.Supplier control |  |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
[5 empty] | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
|  | 6.Initial process flow control |  |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-02-01 W4 to 2018-05-01 W5; 2018-07-01 W1 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W4 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
As per Bhaskar San Frazing cutter is receiving on 3rd WK of March
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
Joint Insp. on 5th Dec
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Lead and Profile error tolerance not fixed for all WEGO parts, Tolerance to be agreed with customer.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
800 NOS PER DAY
QCD-3
FOR MP
FOR MP
Drawing will be release on 8th/9th Dec
T1
PL1
Packing Approval
Bin Order for MP
MP BIN Receive
Joint inspection completed on 15-12-17
Rack rolling m/c received in 2WK of NOV-17
5 sets dispatched on 19-12-2017 ( sch not uploaded in TVS portal)
Frazing cutter receiving on 31-03-2018
MP Starts from 26-02-2018
Upto 2nd WK of April 200 Sets can be dispatch to TVSM as per Grotomat machine capacity
Frazing sample making and Submission
Joint inspection completed on 15-12-17

## MTP WEGO REV-3 after approval (hidden)
MASTER TIMING PLAN |  |  |  |  | Confirmation required on completion | ◎ | [49 empty] | 03 | 2017-11-27 |  |  | Preponement of mp from Mar-17 to Feb-17 | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | Cross Functional Team
[5 empty] | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD | [31 empty] | 02 | 2017-11-11 |  |  | T0 Sample submission date changed from Nov 4th WK to Dec-2 nd WK | [6 empty] | Sreenag |  |  |  | SUNDAR K
Model : | WEGO |  |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 01 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [18 empty] | FC | Praveen San
Year : | 2017-18 | [11 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 00 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [18 empty] | ME | Narendra San
Customer : | TVSM | [54 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [18 empty] | Prod. | Hubli san
SCHEDULE | [5 empty] | Year |  | 2017 | [43 empty] | 2018 | [37 empty] | Quality | Prashanth san
[6 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-02 |  |  |  | 2018-08-03 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[6 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [86 empty] | HT | Ganesh san
[6 empty] | WEGO |  | 2017-12-01 W1: T-0; 2018-03-01 W1: T1; 2018-03-01 W4: PL1; 2018-04-01 W2: MP
[90 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  |  | Dispatch | FC-BLR | PLAN | 2017-12-01 W1: 10; 2018-03-01 W1: 100; 2018-03-01 W4: 300; 2018-04-01 W2: 200; 2018-04-01 W3: 200; 2018-04-01 W4: 400; 2018-05-01 W1: 600; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800; 2018-07-02 W1: 800; 2018-07-02 W2: 800; 2018-07-02 W3: 800; 2018-07-02 W4: 800; 2018-08-03 W1: 800; 2018-08-03 W2: 800; 2018-08-03 W3: 800; 2018-08-03 W4: 800
[7 empty] | ACTUAL | 2017-12-01 W3: 5
[5 empty] | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
[5 empty] | Drawing Release from BWL to BLR | PE-BWL | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Drawing Release from ME BLR to QA, Prod & Pur BLR | ME-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3
[5 empty] | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W1; 2018-01-01 W1
ACTUAL | bar: 2017-08-16 W1; 2017-12-01 W1; 2017-12-01 W3; 2018-01-01 W1
[5 empty] | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2; 2018-02-01 W1; 2018-03-01 W2
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W2
[5 empty] | Sample Making | ME-BLR | PLAN | 2018-01-01 W2: WITH AUTOMATION TRIAL
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-02-01 W3
[5 empty] | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-12-01 W1; 2018-02-01 W4; 2018-03-01 W4; 2018-04-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-12-01 W1
| New mechanism / New structure | Specifications/drawings |  |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W3: set up; 2017-09-16 W4: Trial
[7 empty] | ACTUAL | 2017-03-16 W4: PO DONE
[5 empty] | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5; 2017-10-16 W4 to 2017-11-01 W5
[5 empty] | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W3: set up; 2017-09-16 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W4
[5 empty] | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2018-03-01 W1: set up; 2018-03-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W3
[5 empty] | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 W2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-11-01 W2
|  | 3.Tools & Measurement equipments |  |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
[5 empty] | A'Class tool design (broach,hob shaving) | PE-BWL | PLAN | bar: 2017-07-16 W3 to 2017-09-16 W3
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design ( honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
[5 empty] | A'Class tool design (Frazing cutter ) | PE-BWL | PLAN | 2018-04-01 W1: GROTOMAT m/c to be used for MP till frzaing cutters will come.
ACTUAL | bar: 2017-07-16 W3 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W3
[5 empty] | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
|  | Jigs |  |  | HT jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2017-11-01 W5 to 2017-12-01 W3; 2018-01-01 W1 to 2018-02-01 W1
|  | 3a. Guages |  |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-01-01 W4 to 2018-02-01 W3
|  | 4.Logistics |  |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
ACTUAL | bar: 2017-08-16 W4 to 2017-10-16 W2; 2017-10-16 W4; 2017-12-01 W2 to 2017-12-01 W3
|  | 5.Documentations |  |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
[5 empty] | ②Lot control & Insp check sheets | Production | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
[5 empty] | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W4; 2018-01-01 W1 to 2018-01-01 W2
[5 empty] | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-12-01 W1 to 2017-12-01 W3
[5 empty] | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5
[5 empty] | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W1 to 2017-10-16 W2; 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4
|  | 6.Operator training |  |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W4 to 2017-10-16 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2
|  | Progress of the P-FMEA |  |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
|  | Process design review |  |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
| Capacity | Production capacity |  |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4
| Quality | Quality concept |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W3
|  | Issues with changing point |  |  |  | QA-BLR | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2
|  | Quality managemant plan |  |  |  | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W4
[5 empty] | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W1; 2017-12-01 W1; 2018-02-01 W3
[5 empty] | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W2; 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
[5 empty] | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W2 to 2018-02-01 W2
|  | 2.Prevention |  |  | ①Design verification | NA | PLAN
ACTUAL
[5 empty] | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W5; 2018-01-01 W5; 2018-02-01 W2
[5 empty] | ③QA machine / Pokayoke verification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W5 to 2018-02-01 W1
[7 empty] | ACTUAL | 2017-11-01 W1: List making will comlete in T1 event
[5 empty] | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
ACTUAL | bar: 2017-10-16 W4 to 2017-11-01 W2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2
[5 empty] | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 3.Evaluation of product |  |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
[5 empty] | ②Process capability study | Production,QA | PLAN
ACTUAL
[5 empty] | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W1 to 2017-11-01 W2; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W2 to 2018-02-01 W3
ACTUAL | bar: 2018-02-01 W2 to 2018-02-01 W3
|  | 4.Process verification |  |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2018-01-01 W1 to 2018-01-01 W3
ACTUAL | bar: 2018-01-01 W1 to 2018-01-01 W3
|  | 5.Supplier control |  |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
[5 empty] | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
[5 empty] | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
|  | 6.Initial process flow control |  |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-02-01 W4 to 2018-05-01 W5; 2018-07-01 W1 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  |  | QA | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-02-01 W4 to 2018-03-01 W4
EVALUATION | bar: 2017-11-01 W2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
As per Bhaskar San Frazing cutter is receiving on 3rd WK of March
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
Joint Insp. on 5th Dec
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Lead and Profile error tolerance not fixed for all WEGO parts, Tolerance to be agreed with customer.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
T0 Event Process
200 NOS PER DAY
800 NOS PER DAY
QCD-3
FOR MP
FOR MP
Drawing will be release on 8th/9th Dec
T1
PL1
Packing Approval
Bin Order for MP
MP BIN Receive
Joint inspection completed on 15-12-17
Rack rolling m/c received in 2WK of NOV-17
5 sets dispatched on 19-12-2017 ( sch not uploaded in TVS portal)
Frazing cutter receiving on 31-03-2018
MP Starts from 09-04-2018
Frazing sample making and Submission
ON 10-03-18
ON 27-03-18

## MP readiness (hidden)
Sl No. | MP readiness
1 | " T0 " event will be dispatched in 2nd WK of Dec-17.
2 | TVS will visit MAP-ID BLR for joint inspection of T0 event parts
3 | New drawings will be released in the same week for 'T1' and 'PL1' event
4 | Based on the new drawings sozai to be ordered for T1 and PL1 event in 2nd WK of Dec-17.
5 | Sozai to be receive in 2nd WK of Jan-18 as per new drawings.
6 | T1' event trial starts from 2nd WK of Jan-18 (With automation)
7 | Go Ahead' will receive from customer 3rd WK of Jan-18
8 | T1 event dispatch will be 1st WK of Feb-18
9 | PL1 event diaptch will be 3rd WK of Feb-18.
10 | MP starts from 4th WK of Feb-18.

## MTP WEGO UPDATED REV-1 (2) (hidden)
MASTER TIMING PLAN |  |  |  | Confirmation required on completion | ◎ | [75 empty] | Cross Functional Team
|  |  |  | Confirmation required on change | ○ |  | PLAN |  |  |  |  | PRODUCTS |  | SHAFT CLUTCH, SHAFT COM COUNTER (GI&SI),SAHFT COM REAR WHEEL | [8 empty] | HOD
Model : | WEGO |  |  | Report Required | ☆ |  | ACTUAL | [47 empty] | 1 | 23-08-2017 |  |  | MP qty revised form 400 ~800 per day. | [6 empty] | Sreenag |  |  |  | SUNDAR K | [10 empty] | FC | Praveen San
Year : | 2017-18 | [10 empty] | VOLUME |  | 240,000/ year | [8 empty] | DEPT |  | Project Leader |  |  | FC |  |  | ME |  |  | QA |  |  | PUR |  |  | PROD |  |  | MD | [11 empty] | 0 |  |  |  | INITIAL RELEASE | [6 empty] | Praveen |  |  |  | SUNDAR K | [10 empty] | ME | Narendra San
Customer : | TVSM | [53 empty] | REV | Date |  |  | Remarks | [6 empty] | Prepared |  |  |  | Approved | [10 empty] | Prod. | Hubli san
SCHEDULE |  |  |  |  | Year |  | 2017 | [43 empty] | 2018 | [29 empty] | Quality | Prashanth san
[5 empty] | Month |  | 2017-03-16 |  |  |  |  | 2017-04-16 |  |  |  | 2017-05-16 |  |  |  | 2017-06-16 |  |  |  |  | 2017-07-16 |  |  |  | 2017-08-16 |  |  |  |  | 2017-09-16 |  |  |  | 2017-10-16 |  |  |  | 2017-11-01 |  |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | Prod. | Nagesh San
[5 empty] | WEEK |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
PRODUCTS |  |  | CUSTOMER EVENT | [77 empty] | HT | Ganesh san
[5 empty] | WEGO |  | 2017-11-01 W4: T-0; 2018-02-01 W2: T1; 2018-03-01 W2: PL1; 2018-03-01 W4: MP
[81 empty] | Forging | Manohar San
| MAIN HEADING | SUB HEADING |  | DETAIL OF SUB HEADING | RESPONSIBILITY
| EVENT TRIALS |  |  | Dispatch | FC-BLR | PLAN | 2017-11-01 W4: 25; 2018-02-01 W2: 100; 2018-03-01 W2: 1000; 2018-03-01 W4: 200; 2018-04-01 W1: 200; 2018-04-01 W2: 200; 2018-04-01 W3: 200; 2018-04-01 W4: 400; 2018-05-01 W1: 600; 2018-05-01 W2: 800; 2018-05-01 W3: 800; 2018-05-01 W4: 800; 2018-05-01 W5: 800; 2018-06-01 W1: 800; 2018-06-01 W2: 800; 2018-06-01 W3: 800; 2018-06-01 W4: 800
ACTUAL
|  |  |  | Go Ahead from the customer | SALES | PLAN | 2017-05-16 W1: For T0
ACTUAL | bar: 2017-05-16 W1 to 2017-05-16 W2
|  |  |  | Drawing Release from BWL to BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Drawing Release from ME BLR to QA, Prod & Pur BLR | PE-BWL | PLAN | 2018-02-01 W2: IF NO CHANGE, USE SAME AS T1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Forging Sozai order | FC-BLR | PLAN | bar: 2017-08-16 W1; 2017-12-01 W3 to 2017-12-01 W4; 2018-02-01 W1
ACTUAL | bar: 2017-08-16 W1
|  |  |  | Sozai receive & receiving Insp | PUR-BWL & QA-BLR | PLAN | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-08-16 W4 to 2017-08-16 W5; 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | Sample Making | ME-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 W3; 2018-01-01 W4 to 2018-03-01 W4
ACTUAL
|  |  |  | Final Inspection | QA-BLR | PLAN | bar: 2017-11-01 W1; 2017-11-01 W3; 2018-02-01 W2; 2018-03-01 W2; 2018-03-01 W4
ACTUAL
| New mechanism / New structure | Specifications/drawings |  | Product layout drawings (Proposal,Off tool,Mass production) | R&D,PE
| Technology theme | Functional evaluation |  |  | Testing & Evaluation | PLAN
ACTUAL
|  | Product feasibility |  | Team Feasibility | PE-BWL | PLAN | bar: 2017-03-16 W1 to 2017-03-16 W5
ACTUAL | bar: 2017-03-16 W1 to 2017-03-16 W5
|  | VA/VE・New technology |  |  | PE-BWL | PLAN | bar: 2017-07-16 W2 to 2017-08-16 W2
ACTUAL | bar: 2017-07-16 W2 to 2017-08-16 W2
| Production preparation | Production managemant plan |  | Production managemant plan | New model | PLAN
ACTUAL
|  | 1.Die |  | NA | NA | PLAN | 2017-03-16 W1: OUTSOURCED
ACTUAL
|  | 2.Equipments |  | MTE Rack rolling machine | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: Trial; 2017-09-16 W4: set up; 2017-10-16 W1: Trial
[6 empty] | ACTUAL | 2017-03-16 W4: PO DONE
|  |  |  | Frazing machine | ME-BLR | PLAN | 2017-08-16 W4: set up; 2017-08-16 W5: trial
ACTUAL | bar: 2017-03-16 W2 to 2017-08-16 W5
|  |  |  | Crack testing | ME-BLR | PLAN | 2017-09-16 W1: set up; 2017-09-16 W2: trial; 2017-09-16 W4: set up; 2017-10-16 W1: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W3
|  |  |  | AUTO GRT & OBD GARDING | ME-BLR | PLAN | 2017-11-01 w2: set up; 2017-11-01 W4: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W3
|  |  |  | HOBBING M/C Modification | ME-BLR | PLAN | 2017-11-01 W1: set up; 2017-11-01 w2: trial
ACTUAL | bar: 2017-06-16 W1 to 2017-09-16 W3
|  | 3.Tools & Measurement equipments |  | Tool list | ME-BLR | PLAN | bar: 2017-07-16 W1 to 2017-08-16 W5
ACTUAL | bar: 2017-07-16 W1 to 2017-08-16 W5
|  |  |  | A'Class tool design (broach,hob shaving Frazing cutter and honing tool Grinding wheel, Rack rolls) | PE-BWL | PLAN | 2017-09-16 W4: Rack roll receiving on Sep-17, delay in drawing release.
ACTUAL | bar: 2017-07-16 W3 to 2017-09-16 W3
|  |  |  | A Class tooling arrangement & PO release | ME-BLR | PLAN | bar: 2017-08-16 W2 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W2 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3.Jigs |  | Jigs Manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages design | PE-BWL | PLAN | bar: 2017-08-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-08-16 W1 to 2017-09-16 W3
|  | 3a. Guages |  | Spcl Guages manufacturing | ME-BLR | PLAN | bar: 2017-08-16 W3 to 2017-09-16 W3; 2018-03-01 W1 to 2018-04-01 W1
ACTUAL | bar: 2017-08-16 W3 to 2017-09-16 W3
|  | 4.Logistics |  | Packing specification | FC-BLR | PLAN | 2017-09-16 W3: Packing for T0 trials
[6 empty] | ACTUAL | 2018-01-01 W1: Packing for T1 trials; 2018-02-01 W2: Approval from Customer; 2018-03-01 W2: MP bin receive
|  | 5.Documentations |  | ①Quality Control plan | QA-BLR | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W3; 2018-01-01 W3 to 2018-01-01 W4
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | ②Lot control | Production | PLAN | bar: 2017-10-16 W2 to 2017-10-16 W4; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ③Work standard | PE-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W4; 2017-12-01 W4 to 2018-01-01 W2
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
|  |  |  | ④Appearance standard | Production & QA-BLR | PLAN | bar: 2017-12-01 W1 to 2017-12-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  |  |  | ⑤Work instruction | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W5; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL
|  |  |  | ⑥Quality data checksheet /Date log sheet | Production | PLAN | bar: 2017-10-16 W1 to 2017-10-16 W4; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W2
ACTUAL
|  |  |  | ⑦Maintenance/Pokayoke Checklists | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  | 6.Operator training |  | ①Training for Product/function | Production | PLAN | bar: 2017-09-16 W4 to 2017-10-16 W3; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ②Operator skill evaluation /Skill map | Production | PLAN | bar: 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Progress of the P-FMEA |  |  | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
|  | Process design review |  | Process design /Process flow | PE-BWL | PLAN | bar: 2017-11-01 W5; 2018-01-01 W3 to 2018-01-01 W5
ACTUAL
| Capacity | Production capacity |  | Production capacity | ME-BLR | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W5; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W3
ACTUAL
| Quality | Quality concept |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2017-12-01 W1 to 2017-12-01 W4; 2018-02-01 W4 to 2018-03-01 W2
ACTUAL
|  | Issues with changing point |  |  | QA-BLR | PLAN | bar: 2017-11-01 W4 to 2017-12-01 W1; 2018-01-01 W2 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | Quality managemant plan |  |  | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W3 to 2018-03-01 W1
ACTUAL
|  |  |  | ①marcket claim | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 W1; 2018-01-01 W2 to 2018-01-01 W4; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ② Production line trouble | QA-BLR | PLAN | bar: 2017-10-16 W2 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4
ACTUAL
|  |  |  | ③ Event trouble | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W4; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  | 2.Prevention |  | ①Design verification | NA | PLAN
ACTUAL
|  |  |  | ②SPEC studies/Test result | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2018-01-01 W4 to 2018-01-01 W5; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ③QA machine / Pokayoke velification | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3; 2018-02-01 W3 to 2018-02-01 W4
ACTUAL
|  |  |  | ④Measurement system analysis / Gauge R&R | QA-BLR | PLAN | bar: 2017-11-01 W1 to 2017-11-01 W3; 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Critical elements(FLAP) | QA-BLR | PLAN | bar: 2017-10-16 W3 to 2017-11-01 w2; 2018-01-01 W3 to 2018-01-01 W5; 2018-02-01 W2 to 2018-02-01 W4
ACTUAL
|  |  |  | ⑥QA matrix (if required by customer ) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 3.Evaluation of product |  | ①Verification of process assurance capability(PAC-V) | QA-BLR | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Process capability study | Production,QA | PLAN | bar: 2018-03-01 W1 to 2018-03-01 W4
ACTUAL
|  |  |  | ③Defect study on external and internal | Production,QA | PLAN | bar: 2017-11-01 W1 to 2017-11-01 w2; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W1 to 2018-03-01 W3
ACTUAL
|  |  |  | ④Self-Validation for Mass-production adiness(2DAY) | Production | PLAN | bar: 2018-02-01 W3 to 2018-02-01 W4; 2018-03-01 W2 to 2018-03-01 W3
ACTUAL
|  | 4.Process verification |  | ①QAV-2 | Production,QA,ME | PLAN | bar: 2017-12-01 W4 to 2018-01-01 W3
ACTUAL
|  | 5.Supplier control |  | ①Quality managemant plan | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ②Inspection standards | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ③P-FMEA | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ④Quality Control plan | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑤Process capability study | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  |  |  | ⑥QAV-1･2 | PUR-BWL | PLAN | bar: 2017-09-16 W1 to 2017-09-16 W3
ACTUAL | bar: 2017-09-16 W1 to 2017-09-16 W3
|  |  |  | ⑦Packing specification | PUR-BWL | PLAN | bar: 2017-09-16 W2 to 2017-09-16 W4; 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL | bar: 2017-09-16 W2 to 2017-09-16 W3
|  |  |  | ⑧Measurement data @ each event | PUR-BWL | PLAN | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3
ACTUAL
|  | 6.Initial process flow control |  | Special/Additional control for initial period | Production,QA,Purchasing | PLAN | bar: 2018-03-01 W4 to 2018-07-01 W4
ACTUAL
|  | Quality targets |  |  | QA | bar: 2017-11-01 w2 to 2017-11-01 W4; 2018-01-01 W2 to 2018-01-01 W3; 2018-03-01 W3 to 2018-03-01 W4
EVALUATION
Check By
PROGRESS CHECK (ONCE / 30 DAYS)
Endurence and durability test
QCD-1
DOCUMENT NEED TO RECEIVE FROM BWL TO BLR PE
For WEGO GEARS
For WEGO SHAFTS
QCD-2
For T1 & PL1
For T1 & PL1
JIGS AND FIXTURES FOR MASS PRODUCTION
NOTE: Some technical issue yet to clarify from TVSM. Event progressis based on clarifications & closure.
T1 Event Process
QCD - P& 0
MachineTrail @ Supplier End
If design change then time required for new sozi arrangement
PL1 Event Process
MP
T0 Event Process
Fot m/c trials sozai arrangement
QCD-3
T0 Event Process
T1 Event
PL1 Event
200 NOS PER DAY
800 NOS PER DAY

## Sheet3 (hidden)
Risk Items
1 | For Making Trials 5-6 Weks required
a | All are new parts
b | 9 Pt study to be done (2 times)
c | Require more time for Layout inspection & 9 pt study inspection.
d | If part found NG re-trial to be done
2 | For Sozai arrangement 4-5 Weeks
a | If any drawing change time required for sozai trials
b | Re-make if sozai part found NG