## Q GATE
Q GATE Frequency Based Deliverable Status. | [7 empty] | X | O | Δ |  | Responsibility : Giridhar & Team
[8 empty] | Not Done | Completed | Pending |  | MONTH : JUNE | 2022
| SLNO | ACTIVITIES | Target | Report To | FREQUENCY | Responsibility | Plan | Re Plan | Actual | Status | Remarks
EXTERNAL | 1
2
3
4
5
6
INTERNAL | 1 | Cell Graph Display -Making Shift wise target As per FC plan | 03.06.2022 | Prashanth San | Monthly | Giridhar & Reddy | 03.06.2022 |  | 03.06.2022 | O
| 2 | Comparison of Production output and SAP output punch | 10:30 am/Day | Prashanth San | Daily | Giridhar | 10:30 am/Day |  |  | O | Daily comparision and monitoring.
| 3 | Manpower calculation & planning as per FC plan for next month | 28.05.2022 | Prashanth San | Monthly | Giridhar | 28.05.2022 |  | 29.05.2022 | O
| 4 | Preparation of Monthly shift schedule as per Manpower | 02.06.2022 | Prashanth San | Monthly | Giridhar | 02.06.2022 |  | 30.05.2022 | O | Weekly preparation
| 5 | Q conference data-Summarise the monthly scape data and counter measure for the top defects | 12.06.2022 | Prashanth San | Monthly | Giridhar | 12.06.2022 |  |  | Δ | Under preparation.
| 6 | Preparation of Monthly rework data cost for QA cost calculation | 03.06.2022 | Amar San/Prashanth san | Monthly | Giridhar | 03.06.2022 |  | 03.06.2022 | O | Data shared in Mail
| 7 | Preparation of Monthly Manpower status of Q gate | 03.06.2022 | Amar San/Prashanth san | Monthly | Giridhar | 03.06.2022 |  | 02.06.2022 | O | Data shared in Mail
| 8 | Reporting Q gate Daily Plan vs Act details as per FC plan | 10:30 am/Day | Prashanth San | Daily | Giridhar | 10:30 am/Day |  |  | O | Daily shift wise reporting
| 9 | Business plan activities progress reporting | 1st week of every month | Prashanth San | Monthly | Giridhar | 1st week of every month |  |  | Δ | L4 activities under review
| 10 | DAILY Rejection PPT update for Q gate concern | 5:30pm/Day | Prashanth san | Daily | Giridhar | 5:30pm/Day |  |  | O
| 11 | HOD MEETING Data preparation for Q gate | 5:30pm/Day | Prashanth san | Daily | Giridhar | 5:30pm/Day |  |  | O
| 12 | Daily GPDN K0NA parts rejection analysis & reporting | 4:30pm/Day | CFT | Daily | Giridhar | 4:30pm/Day |  |  | Δ
| 13 | Daily CD Vs OBD graph verification | 08:35 am/Day | Prashanth San | Daily | Giridhar | 08:35 am/Day |  |  | O
| 14 | DAILY Rejection parts analysis & verification with concern section & making scrape note | 2:00pm/Day | Prashanth san | Daily | Giridhar/Reddy/ Concern section | 2:00pm/Day |  |  | O
| 15 | Ensuring the opening stock for Assembly line | 11:00pm/Day | Prashanth San | Daily | Giridhar/Reddy | 11:00pm/Day |  |  | O
| 16 | Daily cell graph updating & verification | 08:40 am/Day | Prashanth San | Daily | Giridhar/Reddy | 08:40 am/Day |  |  | O
| 17 | Q gate consumables stock maintain & indent making | 1st week of every month | Prashanth San | Monthly | Giridhar/Reddy | 1st week of every month |  | 23.05.2022 | O | Indent done for MPI OIL- 07 barrel, Cable ties,Rust oil & Nylon rod
| 18 | Daily Gemba Operation meeting addressing with Top rejection & concerns for daily plan achieve | 09:00 am/Day | CFT | Daily | Giridhar | 09:00 am/Day |  |  | O
Note :- Additional activities which comes as per Require
1 | Training/Refreshing plan for All Assocites on 5s,Basic safety,work condition,DO & DONTS, part handling, inspection,etc
2 | New assocites Skill test and training
3 | Possion test for Repeated customer complaints.
Prepared By |  |  |  | Checked By |  |  |  |  | Approved By

## Calibration -Jun-22
CALIBRATION- FREQUENCY BASED DELIVERABLE STATUS | [7 empty] | NA | X | O | Δ | Responsibility : | Sathish Kumar
[8 empty] | Not Applicable | Pending | Completed | Under process | Month: | 2022-06-01
Category | # | Activity | Target | Report To | Frequency | Responsibility | Plan | Re-Plan | Actual | Status | Remarks / Justification
Calibration | 1 | Daily Budget plan vs actual as per Nyroki plan Updation | Daily | Umasankar san | Daily | Prakash | Daily |  | Daily | Δ
| 2 | Budget Consumption data Compilation | 4th of every month | Management | Monthly | Prakash | 04.06.22 |  | 04.06.22 | O
| 3 | Cost Saving | 5th of every month | Finance | Monthly | Sathish /Prakash | 05.06.22 |  | 06.06.22 | O
| 4 | Cost saving Indent & receive quote & Make Indent (One Month Advance) | 2nd of every month | Management | Monthly | Sathish /Prakash | 02.06.22 | 06.06.22 | 06.06.22 | O
| 5 | Expenses Budget plan vs Actual (MRM ) | 3rd of every month | Management | Monthly | Sathish /Prakash | 03.06.22 |  | 03.06.22 | O
| 6 | Int. Calibration Plan vs Actual | Qty As per plan | Management | Fourth Nightly | Prakash / Sangamesh | 14.06.22 28.06.22 |  |  | Δ
| 7 | External Calibration Plan vs Actual | Qty As per plan | Management | Fourth Nightly | Sathish /Prakash | 14.06.22 28.06.22 |  |  | Δ
| 8 | Calibration MIS Data | 5th of Every month | Management | Monthly | Sathish /Prakash | 05.06.22 |  | 05.06.22 | O
| 9 | AMC Ext | As per plan | Management | As per plan | Sathish | 24.06.22 |  |  | Δ | 1). CAM TESTER AMC & CALIBRATION. 2). XRF GUN ANALYSER CALIBRATION.
| 10 | Making of Indent & Get Approval | Daily /As per requirement |  | Daily | Sathish /Prakash | -- |  |  | Δ
| 11 | Calibration Part Master | As per plan |  | Quarterly | Prakash / Sangamesh | 25.06-22 |  |  | Δ
| 11 | MSA Plan vs Actual | As per plan |  | Fourth Nightly | Prakash / Sangamesh | 16.06.22 30.06.22 |  |  | Δ
| 12 | 5'S in Work zone | Daily |  | Monthly | Prakash / Sangamesh | -- |  |  | Δ
| 13 | Assy gauge validation ( New Addition) | Every fourth night |  | Monthly | Prakash / Sangamesh | 12.06.22 24.06.22 |  |  | Δ
| 14 | Co-relation study ( New Addition) | if any abnormality |  | Immediate act | Prakash / Sangamesh | -- |  | Daily | Δ
| 12 | GAUGE Tray Procurement ( DCM Activity ) Plan preparation. | As per plan |  | Monthly | Prakash / Sangamesh | 10.06.22 |  | 06-062022 | O
| 13 | Gauge Inventory | Quarterly/As per plan |  | Quarterly | Prakash / Sangamesh | NA |  |  | NA
| 14 | Indent plan (Regular as per the Budget) ) | Every week on Monday |  | Weekly | Sathish /Prakash | 06.06.22 13.06.22 20.06.22 25.06.22 |  |  | Δ
| 15 | 100% Master gear wear pattern confirmation Trend & Data Compilation | 3rd week of every month |  | Monthly | Sathish /Prakash | 20.06.22 |  |  | Δ
| 16 | Updation of Gauges Master list for New gauges in Excel | 3rd of every month |  | Monthly | Prakash / Sangamesh | 03.06.22 |  | 03.06.22 | O
| 16 | RGP Preparation & Follow up | As contigency & 10th of Every month |  | As per contigency | Prakash /Sathish | 18.06.22 |  |  | Δ
| 17 | Preparation of Inventory Budget if any | As per plan |  | Once in Six Month | Prakash / Sangamesh | NA |  |  | NA
| 18 | MRN Clearance | Every Thursday |  | Weekly | Sathish /Prakash | 07.06.22 14.06.22 23.06.22 30.06.22 |  |  | Δ
Note :- Additional activities which comes as per Requirement
| 1 | Calibration of Part Master needs to be carried out as per plan
| 2 | Assy Gauges validation -plan needs to be prepare & adhere
| 3 | Co-relation study ( New Addition)
| 4 | Updation of Gauges Master list for New gauges in Excel
Prepared By |  |  | Checked By | [5 empty] | Approved By

## System June-22
Quality Systems Frequency Based Deliverable Status | [7 empty] | NA | X | O | Δ | Responsibility : | Amar Wandre
[8 empty] | Not Applicable | Pending | Completed | Under process | Month: | 2022-06-01
Category | # | Activity | Target | Report To | Frequency | Responsibility | Plan | Re-Plan | Actual | Status | Remarks / Justification
System | 1 | President report 1 (MSI Report) | 4th of Every month | BWL | Monthly | Amar | 04.06.2022 |  | 04.06.2022
| 2 | President report -2 (Quality cost) | 6th of Every month | BWL | Monthly | Amar | 04.06.2022 |  | 04.06.2022
| 3 | KPI planv/s actual updation | 6th of Every month |  | Monthly | Amar | 06.06.2022 |  | 06.06.2022
| 4 | MQCD Finance Data | 6th of Every month | Finance | Monthly | Amar | 07.06.2022
| 5 | MQCD view points review | As per plan |  | Yearly | Amar | 08.06.2022
| 6 | MQC test application form submission | As per plan |  | Yearly | Amar | 10.06.2022
| 7 | Global regulation request form submission | As per plan |  | Yearly | Amar | 08.06.2022
| 8 | MQCD KPI updation in space finder | 10th of Every month | Management | Monthly | Amar | 10.06.2022
| 9 | MIQC kick off meeting | As per plan |  | Yearly | Amar | 10.06.2022
| 10 | BP Lv 4 Activity plan vs actual | 11th of Every month | MRM | Monthly | All concerned | 11.06.2022
| 11 | MRM Preparation | 12th of Every month | Management | Monthly | All concerned | 13.06.2022
| 12 | Kobetsu kaizen preparation /Updation | 14 th of every month | Management | Monthly | All concerned | 14.06.2022
| 13 | Sytem updates | 15 th of every month |  | Monthly | Amar | 15.06.2022
| 14 | Internal audit plan finalization & release | As per plan |  | Yearly | Amar | 16~18.06.22
| 15 | MQCD view points audit | 18 th of every month |  | Monthly | Amar | 18.06.2022
| 16 | Quality Policy updation | As per plan |  | Yearly | Amar | 20.06.2022
| 17 | Scarp disposal review | 20 th of every month |  | Monthly | Amar | 20.06.2022
| 18 | Global regulation request implementation | As per plan |  | Yearly | Amar | 22.06.2022
| 19 | IMS audit closer review | As per plan |  | Yearly | Amar | 30.06.2022
| 21 | Quality Policy updation | As per revision | Management | Half Yearly | Amar | 23.07.21 |  |  | Δ
| 22 | Pocket Guide preparation | FY 21~22 | Management | Yearly | Amar | 27.07.21 |  |  | Δ
Note :- Additional activities which comes as per Requirement
# | 1 | Any Change in 4 Level of documents DCR -Updation & Communication as per requirement
Prepared By |  |  | Checked By | [5 empty] | Approved By

## INPROCESS
IN-PROCESS Quality Frequency Based Deliverable Status. | [7 empty] | X | O | Δ |  | RESP :- BHASKAR SUMAN
[8 empty] | Not Done | Completed | Pending |  | MONTH : JUNE | 2022
| SLNO | ACTIVITIES | Target | Report To | FREQUENCY | Responsibility | Plan | Re Plan | Actual | Status | Remarks
EXTERNAL | 1
2
3
4
5
6
INTERNAL | 1 | For Daily PPT prepration, Top rejection Detail WITH ACTION & C/M. | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 9 AM |  |  | O
| 2 | HOD MEETING PREPRATION ( Major rejection root cause find out and Action Detail Submit). | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 9 AM |  |  | O
| 3 | SCRAP NOTE ENTRY / APPROVAL | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 2 PM |  |  | O
| 4 | REJECTION REVIEW MEETING IN GENBA OF ALL LINES. DRM PREPRATION ( REJECTION & PRODUCTION ENTRY) | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 12 PM |  |  | O
| 5 | REJECTION ANALYSIS AND DETAILS SHARED IN DAILY PPT. | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 9 AM |  |  | O
| 6 | ALL LINE SETTINGS APPROVAL VERIFYIED | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY |  |  | O
| 7 | For Critical parts or major rejection parts control .M/C Parameter checked in shop floor as per TPM check sheet verify as per process sheet followed or not. | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 12 PM |  |  | O
| 8 | CAM ALL LINE DECOMP HT FIXTURE WISE DATA TAKEN & CORRECTION GIVEN IF WE FOUND NG. | Daily | Prashanth San | Daily | BHASKAR SUMAN | DAILY BEFORE 10 AM |  |  | O
| 9 | PRESIDENT REPORT (MSI REPORT WITH TOP 3 REJECTION ANALYSIS) | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 02.06.22 |  |  | O
| 10 | MONTHLY FINANCIAL REPORT (WITH TOP 3 REJECTION ANALYSIS) | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 04.06.22 |  |  | O
| 11 | BAWAL FINANCE REPORT REPORT WITH TOP 3 REJECTION ANALYSIS) | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 05.06.22 |  |  | O
| 12 | ASIA Q REPORT WITH DETAILS REJECTION ANALYSIS | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 05.06.22 |  |  | O
| 13 | FOR RRM MEETING DATA COLLECTION & COUNTERMEASURE VERIFICATION OF IN HOUSE REJECTION & LOT REJECTION. | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 02.06.22 |  |  | O
| 14 | MIS PREPRATION WITH TOP REJECTION ANALYSIS | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 04.06.22 |  |  | O
INTERNAL | 15 | Q CONFRENCE DATA PREPRATION AND ANALYSIS OF TOP-3 REJECTION OF THE MONTH. | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 11.06.22
| 16 | Office Cell board Updating | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 01.06.22 |  |  | O
| 17 | POKA YOKE SHEET VERIFICATION OF ALL SECTION IN SHOP FLOOR. | 2ND week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 09.06.22 |  |  | O
| 18 | PRODUCT AUDIT | 3rd week of month | Prashanth San | Monthly | BHASKAR SUMAN | 15.06.22
| 19 | BP ACTIVITIES | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 1ST WEEK OF THE MONTH
| 20 | COUNTERMEASURE VERIFICATION | second week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 11.06.22
| 21 | PROCESS CAPABILITY STUDY OF MAJOR NG CONTRIBUTING PARTS. | 2ND week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 2ND WEEK OF THE MONTH
| 22 | 9 POINT STUDY OF MAJOR REJECTION PARTS. EX:-GPD K0NA/K1CA,GPDN K0NA,GPDN APACHE,GPD HLX | first week of Month | Prashanth San | Monthly | BHASKAR SUMAN | 17.06.22
| 23 | REJECTION ANALYSIS | MONTHLY | Prashanth San | Monthly | BHASKAR SUMAN | 1ST WEEK OF THE MONTH
| 24 | BUSINESS PLAN DATA AND EVIDENCE PREPARE OR SUBMIT TO CONCERN MEMBER. | MONTHLY /QUATERLY | Prashanth San | QUATERLY | BHASKAR SUMAN | 1ST WEEK OF THE MONTH
| 25 | IATF DATA AND EVIDENCE PREPARED OR SUBMIT TO CONCERN MEMBER. | QUATERLY | Prashanth San | QUATERLY | BHASKAR SUMAN | QUATERLY
| 26 | MQCD DATA AND EVIDENCE SUBMIT | QUATERLY | Prashanth San | QUATERLY | BHASKAR SUMAN | QUATERLY/ AS PER REQUIRMENT
Note :- Additional activities which comes as per Require
1 | N1,N5 & N30 TO BE TAKEN FOR NPD LINES / MACHINE APPROVALS
2 | CP,CPK DATA TAKEN FOR MAJOR ISSUES.
3 | ALL TEETH OBD ,CD & PCD TO BE TAKEN FOR GPDN KONA PARTS
4 | ANY MAJOR LINE BREAKDOWN MACHINE VERIFICATION FOR QUALITY CONTROL.
5 | IF ANY CUSTOMER CONCERN THEN IMMEDIATE WIP PARTS & MACHINE WILL VERIFY.
Prepared By: Bhaskar suman |  |  |  | Checked By:- Prashanths san |  |  |  |  | Approved By:- Padavala Umashankar san

## NPD
NEW PRODUCT DEVELOPMENT QUALITY FREQUENCY BASED DELIVERABLE STATUS | [7 empty] | X | O | Δ | Responsibility : SUSHIL /SHIVA
[8 empty] | Not Done | Completed | Pending | MONTH : JUN-22
| SL NO | ACTIVITIES | TARGET | REPORT TO | FREQUENCY | RESPONSI BILITY | PLAN | RE PLAN | ACTUAL | STATUS | REMARKS
INTERNAL | 1 | Morning meeting with QA team | 8.30 am/day | Prashanth san | Daily | Sushil/Shiva | Daily | -- | -- | --
| 2 | NPD slide Updation for Daily PPT | 9.30 am/day | Prashanth san | Daily | Sushil/Shiva | Daily | -- | Daily | O
| 3 | External IPP Status to be share to All concerns | Monthly Once | Prashanth san | Monthly Once | Shiva | Monthly Once | -- | -- | --
| 4 | K3CA -QCD proposal & 0' documents preparation & internal review | As per Sales & FC plan | Prashanth san | As per Sales & FC plan | Sushil | 04.06.2022 |  | 04.06.2022 | O
| 5 | K0PG QCD-3 documents preparation & Internal review evaluation | 23.06.2022 | Prashanth san | As per FC plan | Sushil/Shiva | 22.06.2022
| 6 | HLX 125 QCD1&2 documents preparation & internal review QCD evaluation is planned | 9.06.2022 | Prashanth san | As per FC plan | Sushil/Shiva | 08.06.202 |  | 09.06.2022 | O
| 7 | Ntorq QCD 1& 2 documents preparation & internal review QCD evaluation is planned | 15.06.2022 | Prashanth san | As per FC plan | Sushil/Shiva | 14.06.2022
| 8 | K0NA QCD -3 documents preparation & internal rev-1 QCD evaluation is planned | 11.06.2022 | Prashanth san | As per FC plan | Shiva /Sushil/Prasanna | 10.06.2022
| 9 | Wego ECN QCD 3-3 documents preparation & internal rev-1 QCD evaluation is planned | 16.06.2022 | Prashanth san | As per FC plan | Shiva /Sushil/Prasanna | 15.06.2022
| 10 | K0PH PP1-1 samples submission (mass production common parts ) | 06.06.2022 | Prashanth san | As per FC plan | Shiva /Sushil/Prasanna | 06.06.2022 |  | 07.06.2022 | O
| 11 | K3CA Electrode & dies inspection is planned as per plan |  | Prashanth san | As per FC plan | Prasanna
12
13
14
15
| 16 | +
17
18
19
20
Note :- Additional activities which comes as per Require
1 | Additional 9 points inspection & HT trails.
2 | Customer related noise parts inpsection.
| PREPARED BY |  |  | CHECKED BY |  |  |  |  | APPROVED BY