## MANPOWER
|  |  | RULE |  |  |  | MANPOWER MONITORING AND IMPROVEMENT
Rule No. |  |  | Issue | Rev. | Date | Page
ISD-MS-004 |  |  | 01 | 00 | Dec.2016 | 01 of 01
| S No. | Activity |  |  |  | Frequency | Responsibility | Check point
| 1 | PLAN OR TARGET SETTING
|  | 1.1) PDE depp. Will released the requierd manpower for each section according to capacity and customer requierment of month (Evevry month) . |  |  |  | Monthly | PDE/Prod. | Capa. Conf. Meeting
|  | 1.2) PDE depp. Will communicate the information through Capacity coinfirmation meeting |  |  |  | Monthly | PDE/Prod. | Capa. Conf. Meeting
|  | 1.3)Requierd Manpower released by PDE will be target (Plan) for every section |  |  |  | Monthly | Section head (Prod.) | MP Monitoring sheet
|  | 1.4) Production depp. Has to be updated this released manpower in there manpower controling sheet as plan manpower |  |  |  | Monthly | Section head (Prod.)
| 2 | DATA MONITORING
|  | 2.1)Production depp. Has to be recorded the used manpower and overtime section wise/ day wise |  |  |  | Daily for last working day | Sec. Head (Prod.) | MP Monitoring sheet
| 3 | ANALYSIS
|  | 3.1) If Actual head count of day is more than target ,we have to analyz the data and find the gap between plan head count and actual head count |  |  |  | Daily | Shift Incharge (Prod.) | MP Monitoring sheet
|  | 3.2) if actual head count of month is more then plan ,we have to analyz the detail through WHY-WHY & PDCA format(ISF-MS-026) |  |  |  | Monthly | Section Head (Prod.) | Format (ISF-MS-0026)
|  | 3.3) if actual over time of month is more then plan ( decided by concerned section on the basis of last year data) ,we have to analyz the detail through WHY-WHY & PDCA format(ISF-MS-026) in a seprate sheet |  |  |  | Monthly | Section Head (Prod.) | Format (ISF-MS-0026)
| 4 | IMPROVEMENT
|  | 4.1) Need to improve the utilization of resources by various kaizen and Countremeasure if actual head count is more then plan and it should be pioritize on the basis of their impact on Line performance |  |  |  | Every month | Section head (Prod.) | Concerned Section PRM
|  | 4.2)We have to fill the actual reason and countremeasure in MP monitoring sheet ,where actual head count is more then plan for any working day |  |  |  | Daily | Shift Incharge (Prod.) | MP Monitoring sheet
|  | 4.1) Need to decrease the overtime by various kaizen and Countremeasure if actual overtime is more then plan and it should be pioritize on the basis of their impact on Line performance |  |  |  | Every month | Section head (Prod.) | Concerned Section PRM